## Timeline Details
GSS25871-STRAT_PLAN
Strategic Planning Process
Appendix B - Budget Timeline Details
Coordinate and Facilitate the Multi-Council Leadership Group Meetings
A. Plan, facilitate and convene at minimum one meeting, but potentially two meetings, with the Multi-Council Leadership Team, which shall consist of representatives from the Developmental Disabilities Council (DDC), State Council for Persons with Disabilities (SCPD), and the Governor’s Advisory Council for Exceptional Citizens (GACEC) to discuss high-level concerns/themes in the Delaware disability community.
B. Contractor is responsible for working with DDC staff and Council members to identify and reach out to invitees with an invitation to participate.
C. Contractor is responsible for tracking invitee RSVPs and following up with individuals who do not RSVP.
D. Contractor is responsible for securing fully accessible meeting locations for all meetings. This can be via zoom if unable to find a date agreeable to meet in person at the DDC Conference room.
E. If meeting location is not already known to Council and staff as being fully accessible, a meeting location accessibility check will be coordinated by the contractor.
F. Meeting location accessibility check will include contractor, representative from meeting space, and/or a member of DDC staff/Council member.
G. Outcomes from these sessions shall be recorded by the contractor and shared with the Multi-Council Leadership Team in the form of a brief summary report.
H. Ideas in the report will be used by the DDC to explore if/how the ideas shared fit in with the DDC’s federal grant areas of emphasis.
I. Findings from the February 2025 meetings will also be used to inform the contractor’s efficient facilitation of the Focus Groups to be held in Mid-May to late June 2025 (see item III).
Survey Distribution, Marketing and Tracking
A. Following the multi-Council leadership team’s meeting and input, contractor will use this information along with existing survey templates (available to successful contractor) to create, distribute, and track responses from a consumer survey to establish most effective distribution mechanism (e.g. Survey Monkey, Constant Contact, etc.).
B. Create marketing/promotional materials encouraging/reminding people to take the survey, these may include, but are not limited to: email reminders to established listservs that will be made available to the contractor, social media posts pre-written by the contractor for distribution either by contractor or community partners, press releases, etc.
C. Provide disaggregated data from the survey to the DDC after it is closed to further input.
D. Disaggregated data will be provided to the DDC within two weeks of the close of the survey.
Focus Groups
A. Contractor will work with DDC staff and Council to plan and facilitate a minimum of six Focus Groups, to be held virtually – ensuring participation from all three counties with three occurring during business hours and three occurring at night.
B. Contractor will work with DDC staff and Council to identify and send invitations to Focus Group participants, ensuring that participants represent a diverse range of races and ethnicities, types of disability (self or family), and geographic locations within each county.
C. Contractor will track all RSVPs and will follow up with invitees who do not RSVP.
D. Contractor will track, respond to, and coordinate all requests for reasonable accommodations from invitees with disabilities, to include making reservations for requested reasonable accommodation services/products and payments to the providers of these services/products. Examples of reasonable accommodations could include sign language interpreters, closed captioning, etc.
E. Focus group participants will be asked for their input on the major themes identified by the Multi-Council Leadership Team, as described in Item I, as well as any other ideas that they would like to see the DDC focus on.
F. Contractor shall track attendance on the day of each Focus Group via Zoom, which will be shared with the Council after the Focus Group via inclusion in each session’s narrative report to the DDC’s Social Services Administrator. To secure required demographic information, contractor shall ask the below information during registration for the virtual Focus Groups that includes information: participants’ name, designation (e.g., person with a disability, family member of a person with a disability, service provider, other), county, and email address. 15 minutes will be allotted at the end of each meeting to administer a required survey to collect other required data for federal reporting to include information such as age, gender, race, ethnicity, sexual orientation and gender identity data. A survey link will be provided by the DDC staff to the contractor.
G. Contractor will record and report all input from Focus Group participants through a summary report to the DDC for each session (audio recording and/or use of a scribe is recommended to ensure that all comments are captured while contractor is busy facilitating the discussion).
H. Contractor’s summary report to Council from each session will include Attendee data), date, areas of concern shared by participants, new ideas identified by participants, other information the contractor feels would be relevant to the DDC.
I. Summary reports for each session are due to the DDC’s Social Services Administrator within two weeks of the date of each Focus Group.
Initial Public Forums
A. Contractor will plan, coordinate, facilitate, market, and publicize a series of virtual Public Forums (a minimum of six Public Forums, to be held virtually – ensuring participation from all three counties with three occurring during business hours and three occurring at night) to seek the public’s initial input on the development of the DDC’s 2027-2031 State Plan.
B. Contractor will work with DDC staff and Council to identify community partners to assist with publicizing the Public Forums.
C. Contractor will create marketing materials for Public Forums, such as flyers, pre-written social media posts, press releases, etc.
D. Contractor will reach out to identified community partners and request their assistance with sharing information about upcoming Public Forums, as well as making materials available to DDC staff and members for further distribution opportunities.
E. Contractor will track attendance on the day of each Public Forum via Zoom, which will be shared with the Council after the Focus Group via inclusion in each session’s narrative report to the DDC’s Social Services Administrator. To secure required demographic information, contractor shall ask the below information during registration for the virtual Public Forums that includes information: participants’ name, designation (e.g., person with a disability, family member of a person with a disability, service provider, other), county, and email address. 15 minutes will be allotted at the end of each meeting to administer a required survey to collect other required data for federal reporting to include information such as age, gender, race, ethnicity, sexual orientation and gender identity data. A survey link will be provided by the DDC staff to the contractor.
F. Public Forum attendees will be asked for their input on the major themes previously identified as a starting point by the multi-Council leadership team as well as those identified by Focus Groups (see items I and III).
G. Contractor will record and report all input from Public Forum participants through a summary report to the DDC for each session (audio recording and/or use of a scribe is recommended to ensure that all comments are captured while contractor is busy facilitating the discussion).
H. Contractor’s summary report to Council from each session will include attendee data, areas of concern shared by participants, new ideas identified by participants, other information the contractor feels would be relevant to the DDC in planning for their next Strategic Plan.
I. Contractor will submit summary reports for each session to the DDC’s Social Services Administrator within two weeks of each Public Forum.
Strategic Planning Retreat Planning
A. Contractor will begin planning the DDC’s Strategic Planning Retreat, which shall be held in the month of October for a minimum of one 6-hour day to include a light breakfast and lunch for all participants taking into account all dietary needs with input from DDC staff. As a part of this work:
B. Contractor will work with DDC staff to identify all Council members and their contact information.
C. Contractor will create an invitation for all Council members and distribute the invitation in both email and mail form.
D. Contractor will track all RSVPs, ensuring that the RSVP date is in keeping with venue food and beverage deadlines.
E. Contractor will track all RSVPs and will follow up with all invitees who do not RSVP.
F. Contractor will respond to, track, and coordinate all requests for reasonable accommodations from invitees with disabilities in a timely manner, to include making reservations for requested reasonable accommodation services/products and payments to the providers of these services/products. Examples of reasonable accommodations could include, but are not limited to, provision of sign language interpreters, providing large print materials, securing DART Paratransit tickets for registered riders or coordinating other accessible transportation, honoring special dietary needs, provision of a quiet room in the meeting location for individuals who live with sensory difficulties, provision of a personal care room in the meeting location to ensure privacy, etc.
G. Contractor will secure a fully accessible meeting location- if the meeting location is not already known to be accessible due to previous use of the location by the DDC, a meeting to determine accessibility will be made by the contractor and will include a site visit with the contractor, proposed meeting location representative, and a member of DDC staff and/or Council.
H. Contractor will ensure that all logistics are handled with the venue, to include food and beverage, AV (laptop, projector, screen, microphones), setup and tear down.
I. Contractor will provide copies of all previous reports from the Multi-Council Planning Meetings, Focus Groups, and Public Forums to all members of the Council who RSVP that they will attend the Strategic Planning Retreat.
J. Contractor will provide pens, sharpened pencils, notepads, easels, and markers for the day of the retreat (estimate- one box each pens (black) and sharpened pencils, twenty to twenty-five 5” x 7” size legal pads, five Post it Note easels, four boxes of markers).
Strategic Planning Retreat for DDC Members
A. Contractor will ensure that all requested reasonable accommodation arrangements are confirmed and ready to go prior to the day of the Strategic Planning Retreat.
B. Contractor will handle all “day-of” logistics, to include, but not limited to, coordination of food and beverage service (as previously arranged per Item V), AV requirements are good to go (laptop, projector, screen, microphones- as previously arranged per Item V), ensuring confirmed reasonable accommodations requests are being honored, making sure attendees sign in, distributing copies of materials and supplies to members (e.g. pens, pencils, notepads), and recording the proceedings and/or providing a scribe to ensure all information shared is accurately captured.
C. Contractor will fully facilitate the Strategic Planning Retreat, which will include guiding the discussion, pointing out information from the previous events, keeping the attendees on track, ensuring that all goals and objectives take cultural and linguistic competence into consideration, assisting members in identifying a targeted disparity objective, and assisting members with culling down all of the information previously gathered into no more than four Goals with no more than two Objectives under each Goal.
D. Contractor will track attendance on the day of the Strategic Planning Retreat using a sign in sheet, which will include areas for member’s names, and any UPDATES to their address, phone number and/or email address.
E. Strategic Planning Retreat attendees will be asked to review data from previous events (Multi-Council Leadership Meeting, Focus Groups, Public Forums) and use this information to develop no more than four Goals with no more than two Objectives under each Goal.
F. All Goals and Objectives must be in keeping with the DDC’s federal grant requirements and areas of emphasis, which can be determined through discussion with DDC members and staff, as well as the Council’s Technical Assistance (TA) provider, the Information and Technical Assistance Center for Councils on Developmental Disability (ITACC).
G. Contractor will record and report all input from Strategic Planning Retreat participants through a summary report to the DDC (audio recording and/or use of a scribe is recommended to ensure that all comments are captured while contractor is busy facilitating the discussion).
H. Contractor’s summary report should include attendee data (from sign in sheet), date, location, areas of concern shared by participants, new ideas identified by participants, and most importantly, the FINAL determination of the Council on no more than four Goals with no more than two Objectives under each Goal.
I. Contractor will submit a summary report from the DDC’s Strategic Planning Retreat to the DDC’s Social Services Administrator within two weeks of the Retreat.
J. Findings from the Strategic Planning Retreat will be used to create the first draft of the Five-Year Strategic Plan, which will then go through the public notice process.
Public Forums to Review Draft Stateigc Plan, Round 2
Note: Following the Strategic Planning Retreat, and after the contractor provides the Strategic Planning Retreat Summary Report (see item VI i) the DDC Social Services Administrator will create a draft of the report for a second round of public comment (45 days is required). The draft of the Strategic Plan will be available to the public for review on our DDC website, with staff’s contact information provided for feedback. Public forums are also required, virtually, within the 45-day public comment period. The contractor will be responsible for coordinating and facilitating this second round of Public Forums, as well as providing a summary report for the DDC Social Services Administrator within two weeks of each Public Forum. Public forums should be completed no later than mid-December, 2025.
A. Contractor will plan, coordinate, facilitate, market and publicize a series of virtual Public Forums (a minimum of six Public Forums, to be held virtually – ensuring participation from all three counties with three occurring during business hours and three occurring at night) to seek the public’s input on their DRAFT 2027-2031 Strategic Plan.
B. Contractor will work with DDC staff and Council to identify community partners to assist with publicizing the Public Forums.
C. Contractor will create marketing materials for Public Forums, such as flyers, pre-written social media posts, press releases, etc.
D. Contractor will reach out to identified community partners and request their assistance with sharing information about upcoming Public Forums, as well as making materials available to DDC staff and members for further distribution opportunities.
E. Contractor will track attendance on the day of each Public Forum by asking questions via registration for the virtual forum which includes information: participants’ name, designation (e.g., person with a disability, family member of a person with a disability, service provider, other), county, and email address. 15 minutes will be allotted at the end of each meeting to administer a required survey to collect other required data for federal reporting to include information such as age, gender, race, ethnicity, sexual orientation and gender identity data. A survey link will be provided by the DDC staff to the contractor which will be shared with the Council after the Focus Group via inclusion in each session’s narrative report to the DDC’s Social Services Administrator.
F. Public Forum attendees will be asked for their input on the major themes previously identified as a starting point by the multi-Council leadership team as well as those identified by Focus Groups.
G. Contractor will record and report all input from Public Forum participants through a summary report to the DDC for each session (audio recording and/or use of a scribe is recommended to ensure that all comments are captured while contractor is busy facilitating the discussion).
H. Contractor’s summary report to Council from each session will include attendee data (from sign in sheet), date, location, areas of concern shared by participants, new ideas identified by participants, other information the contractor feels would be relevant to the DDC in planning for their next Strategic Plan.
I. Contractor will submit summary reports for each session to the DDC’s Social Services Administrator within two weeks of each Public Forum.
J. Summary/Narrative Reports on Public Forum data must be provided to the DDC Social Services Administrator prior to the DDC’s January 2026 meeting so that the Council may review the input on the draft Strategic Plan and vote accordingly.
Ongoing/Miscellaneous Requirements
A. Contractor will provide all narrative reports and data within the specified time frame. Failure to provide required reports may result in payment to contractor being held back until the required reports are submitted.
B. Contractor will submit all expense reports for the previous month’s expenses to both the DDC and GSS by the 15th of each month.
C. Contractor will inform DDC Social Services Administrator immediately of any unexpected adverse events which will impact their planning and execution of this Scope of Services.
D. Contractor will notify both DDC and GSS of any requested budget line-item changes, which will necessitate an amendment.
E. All contract staff and sub-contractors should be identified at the time the potential contractor’s proposal is submitted.
F. Contractor will utilize respectful, appropriate language at all times, and will observe the rules of disability etiquette (DDC staff will train the contractor, if need be).
G. Contractor will respond promptly to any requests for information or data from the DDC and/or its staff.
H. DDC reserves the right to request the contractor to attend/present at one or more of their monthly meetings held on the second Wednesday of the month every month except for July and December for 2 hours.
I. Quick Guide to anticipated meetings/events/items that require tracking that will need to be planned, coordinated and facilitated by the contractor/organization:
· Public Forums – 6 (3 during business hours and 3 in the evening with equal representation from each county).
· Focus Groups – 6 (3 during business hours and 3 in the evening with equal representation from each county).
· Survey – 1, based on previous surveys and other examples, to be open April to June 2025
· Strategic Planning Retreat – 1 (centrally-located in Kent County- October 2025 with availability for hybrid
J. Anticipated contractor staff roles (individuals may fill more than one role):
· Main contractor
· Facilitator
· Event Planner
· Administrative Support Professional for scribing, copying, assisting with planning for reasonable accommodations, following up, assisting with data collection, etc.
· Marketing/Public Relations Staff
K. Summary Reports Required:
· Within two weeks of each event to the DDC Social Services Administrator
· Must include participant feedback, data from sign in sheets, other information as specified in Scope for each event.
· Need not be lengthy, as long as they provide attendee data and feedback
· May be submitted in bullet point format
· May be submitted via email
· A draft version of the findings must be provided to the DDC staff by end of first week in January so that the draft can be reviewed by Council and go out for the first round of 45 Day Public Comment by mid-January. The draft must be approved by Council at the January meeting and then put out for Public comment. Once the first 45 days is completed, if any comments are received back, those comments must go to Council to review and vote upon. If significant changes are made, then it may need to go out for an additional comment period. (this timeframe in total could be from mid January for the first round of public comment through the above steps to potentially late April.)
· A final cumulative summary report with all information must be provided at the end of the project no later than June 5, 2026. This will allow for the Council to approve the final version of the State Plan before entering and meeting the below deadline. This will be utilized for the Executive Director to input into the federal reporting system in late June into July to ensure meeting the August 15, 2026 deadline.
L. Expense Reports Required:
Expense reports are due to the DDC and GSS by the 15th of the month for each previous month’s contract expenses. Final expense report will be processed once all final deliverable have been received and have been approved by the DDC Social Services Administrator and Executive Director.
M. Possible Supplies Required/Suggested:
· Pens, Black, one box
· Pencils, sharpened, one box
· Notepads, 5” x 7”- thirty to fifty
· Post It Note Easels- five to six
· Markers, assorted permanent- four to five boxes
· Hand sanitizer- four bottles
· Tissues- five to ten boxes
· Stapler- one
· Staple puller- one
· Scotch Tape Dispenser- two or three
· Laptop- one
· Copier paper- Use judgement based on the number of materials you will be printing for the Planning Retreat
· Regular access to computer or tablet
· Regular access to internet
· Regular access to phone
· Regular access to reliable transportation
· Access to printer or printing facility such as Staples, as needed
· Access to copier or copy facility, as needed
· Microsoft Publisher or other design software, for flyers and announcements
· Microsoft Word or similar, to generate documents
· Adobe or similar software- ability to generate PDF and JPG files on your computer

## Budget Timeline
GSS25871-STRAT_PLAN
Strategic Planning Process
Appendix B - Budget Timeline
Milestone | Budget Percentage
Multi-Council Leadership Group Meeting
Survey Distribution, Marketing and Tracking
Focus Groups
Initial Public Forums
Strategic Planning Retreat Planning
Strategic Planning Retreat for DDC Members
Public Forums to Review Draft Stateigc Plan, Round 2
Ongoing/Miscellaneous Requirements

## Budget
GSS25871-STRAT_PLAN
Strategic Planning Process
Appendix B - Budget
BUDGET ITEMS | FEDERAL FUNDS | MATCH FUNDS | TOTAL
1. Total Salaries | $30,000 | 10000 | 40000
2. Other Employment Costs
a. Hospitalization
b. FICA
c. Unemployment Comp.
d. Workers Comp
e. Other (specify)
Total other EMPLOYMENT COSTS:
3. Travel
a. Mileage
b. Other (Specify)
Total TRAVEL COSTS:
4. Contractual services
a.
b.
c.
Total CONTRACTUAL SERVICES:
5. Supplies/Material
a.
b.
c.
Total SUPPLIES/MATERIALS:
6. TOTAL Volunteers
GRAND TOTAL: | $30,000 | 10000 | 40000