STATE OF DELAWARE

|  | DELAWARE HEALTH AND SOCIAL SERVICES OFFICE OF THE SECRETARY 1901 N. DuPont Highway New Castle, DE 19720 |  |  |
| --- | --- | --- | --- |

Technical Requirements Appendix B

REQUEST FOR PROPOSAL NO. HSS-24-052

FOR

Preadmission Screening and Resident Review (PASRR) - Web Based System and Services

Approved Business Case Number: BC0002582 July 15, 2024

Table of Contents

1	Project Overview	5

1.1	Background and Purpose	5

2	DHSS Program and System Overview	7

2.1	DHSS	7

2.2	The Division	7

2.2.1	Information Resource Management (IRM)	8

2.2.2	Department of Technology and Information (DTI)	9

2.2.3	Division Business Analyst Group	9

3	DHSS Responsibilities	10

3.1	Staffing Roles	10

3.1.1	Project Organization Chart	11

3.2	DHSS Staff Participation	11

3.3	Resource Availability	12

3.4	Change Control	12

3.5	Deliverable Review	12

3.6	Implementation	12

4	Contractor Responsibilities/Project Requirements	13

4.1	Staffing	21

4.1.1	Project Director Requirement	22

4.1.2	Project Manager Requirement	22

4.1.3	Project Help Desk Staff Requirement	22

4.2	Project Management	23

4.3	Requirement to Comply with HIPAA Regulations and Standards	23

4.4	Security Requirements	24

4.4.1	Authorizations	24

4.4.2	Architecture Requirements	24

4.4.3	DHSS Hosting Requirements	25

4.4.3.1	Requirement to Comply with State Policies and Procedures	25

4.4.3.2	Standard Practices	26

4.4.3.3	Confidentiality and Data Integrity	26

4.4.3.4	Security Controls	26

4.4.3.5	Cyber Security Liability	26

4.4.3.6	Information Security	26

4.4.3.7	Mandatory Inclusions	27

4.4.3.7.1	Network Diagram	27

4.4.3.7.2	List of Software	27

4.4.3.7.3	3rd Party Authentication	27

4.4.3.7.4	Password Hashing	27

4.4.3.7.5	Data Encryption	27

4.4.3.7.6	Securing DHSS Data	27

4.4.4	Mandatory Inclusions for Cloud/Remote Hosting	27

4.4.4.1	Network Diagram	27

4.4.4.2	List of Software	28

4.4.5	DTI’s Terms and Conditions Agreement	28

4.4.5.1	Agreement Exceptions	28

4.4.6	Subcontractor Requirements	29

4.4.7	Standard Practices	29

4.4.8	Additional Security Requirements	29

4.4.8.1	Encryption of Data at Rest	29

4.4.8.2	Encryption of Data in Transit	29

4.4.8.3	DHSS Data Rights	30

4.4.9	UAT and Training Environments	30

4.4.10	Masking of Production Data in Lower Environments	30

4.4.11	Offsite Project Work	30

4.4.12	Offshore Prohibitions	32

4.4.13	Other Technical Considerations	32

4.5	Reporting	32

4.6	Performance	32

4.7	Customizable COTS Solutions	32

4.8	Backup and Recovery	33

4.9	Disaster Recovery	33

4.10	Specific Project Tasks	33

4.11	Project Deliverables	34

4.11.1	Deliverable Review Process	34

4.11.2	Project Deliverables by Phase	34

4.11.2.1	Phase 1	36

4.11.2.2	…………………………………………………………………………………38

4.11.2.3	Phase 3 - Development	39

4.11.2.4	Phase 4	39

4.11.2.5	Phase 5	40

4.11.2.6	Phase 6 and Phase 7	40

4.12	Project Expectations	41

4.12.1	Site Requirements	41

4.12.2	DHSS Hosted Solutions	41

4.12.3	Remotely-Hosted Solutions	43

4.12.4	Environment Responsibilities	43

4.12.5	Unit Testing	43

4.12.6	System Integration Testing	43

4.12.7	User Acceptance Testing (UAT)	43

4.12.8	Production Implementation	44

4.12.9	Legacy Data Conversion	44

4.12.10	Training	45

4.12.10.1	System User	45

4.12.10.2	Technical	45

4.12.11	Maintenance and Operations (M&O)	46

4.12.12	Documentation	47

4.12.13	Software Escrow Agreement	47

4.12.14	Copyrighted/Proprietary Software Inclusion	47

4.12.15	Miscellaneous Requirements	47

5	Proposal Evaluation/Contractor Selection	48

5.1	Process	48

5.2	Proposal Evaluation and Scoring	48

5.2.1	Mandatory Requirements	48

5.2.2	Technical Proposal Scoring	49

5.2.3	Business Proposal Consideration	49

5.2.4	Contract Negotiation	49

6	Contractor Instructions	50

6.1	Submission Information	50

6.1.1	RFP and Final Contract	50

6.1.2	Proposal and Final Contract	50

6.1.3	Modifications to Proposals	50

6.1.4	Alternative Solutions	50

6.2	Technical Proposal Contents	51

6.2.1	Transmittal Letter (Section A)	51

6.2.2	Technical Proposal Required Forms (Section B)	51

6.2.3	Executive Summary (Section C)	52

6.2.4	Contract Management Plan (Section D)	52

6.2.5	Project Requirements (Section E)	54

6.2.6	Staff Qualifications and Experience (Section F)	54

6.2.7	Firm Past Performance and Qualifications (Section G)	54

6.2.8	Policy Memorandum Number 70 (Section H)	55

6.2.9	RFP Exhibits (Section I)	55

6.3	Business Proposal Contents	55

6.3.1	Project Cost Information (Section J)	55

6.3.2	Software and Hardware Information (Section K)	55

6.3.3	Contractor Stability and Resources (Section L)	56

7	Terms and Conditions	57

7.1	Payment for Services Rendered	57

7.2	Contractor Personnel	57

7.3	Funding	58

7.4	Confidentiality	58

7.5	Contract Transition	58

7.6	Professional Services Agreement (PSA) Template	58

7.7	Contract Amendments	58

8	Exhibits	59

A.	General Terms and Conditions	61

B.	Certification Sheet and Statement of Compliance	65

C.	Website Links (in alphabetical order)	69

D.	Key Position Resume	71

E.	Project Cost Forms	73

F.	Mandatory Submission Requirements Checklist	84

G.	Crosswalk of RFP Section 4	87

H.	Contractor Project Experience	89

I.	Deliverable Acceptance Request (DAR)	91

J.	Contractor Contact Information	93

K.	Criminal Background Check Instructions	95

L.	CMS Certification	96

M.	2015 PASRR National Report	97

N.	Delaware Medicaid State Plan	107

O.	Review of State PASRR	108

P.	State Nursing Facility Medical Necessity Criteria	109

Q.	Quality and Performance Reporting	110

# Project Overview

## Background and Purpose

The State of Delaware (State), Department of Health and Social Services (Department or DHSS), Division of Medicaid and Medical Assistance (DMMA) wishes to execute a contract for professional services with a primary Contractor (Contractor) to procure a web-based Preadmission Screening and Resident Review (PASRR) system. This request for proposals (“RFP”) is issued pursuant to 29 Del. C. §§ 6981 and 6982.

Pre-admission Screening and Resident Review (PASRR) described in 42 C.F.R. §§ 483.100 through 483.138 is a federally required process to screen and evaluate all individuals, regardless of their payer source, who may admit to a Medicaid certified Nursing Facility (NF).  Individuals are screened for Mental Illness (MI), Intellectual or Developmental Disability (IDD), or Related Conditions (RC), (collectively, MI/IDD/RC). This Federal mandate was implemented as part of the 1987 Omnibus Reconciliation Act (OBRA), also known as the Nursing Facility Reform Act of 1987 to reduce or eliminate inappropriate placement of individuals with MI/IDD/RC in Medicaid certified NFs.  

The PASRR Level I (LI) process determines whether there is a suspicion of a PASRR disability, MI/IDD/RC, and if so, an in-depth Level II (LII) evaluation is required. If evidence of MI/IDD/RC exists, the Level II evaluation will determine whether the individual meets the Delaware Level of Care (LOC) criteria for placement in a NF.  In addition, the Level II will identify appropriate Specialized Services (SS) and Rehabilitative Services (RS) that will be needed if the individual enters a NF, and Community Placement Supports (CPS) that would be needed if/when the individual has potential for placement or transition to a lower level of care. NFs are prohibited from admitting individuals with MI/IDD/RC before the PASRR Level I and Level II are completed.

Delaware’s current contract for PASRR was implemented on March 15, 2020.  The original contract was for Level I & II PASRR activities. Specialized Service monitoring was added by an amendment effective 3/15/23 that monitors the care planning process and reviews evidence of delivery of Specialized Services as well as a streamlined functionality for payment authorization for approved NF stays to certified Medicaid Nursing facilities in Delaware.

Delaware’s PASRR program has undergone changes and innovations have been added to the contract.  The current program includes:

- A 24/7 web-based system that is available for hospitals, NFs, and other community provider organizations to gain access by setting up secure user IDs for appropriate staff members.

- Immediate access for viewing, downloading, and printing of PASRR outcomes and Summaries of Findings for all authorized system users, upon completion of PASRR activity by the Contractor.

- Quality reviews of 2% of all Level I outcomes for quality, errors, identification of concerns.

- A web-based system that links PASRR information to the Agency’s Medicaid eligibility determination processes.  This process includes:

  - A system that requires NFs to submit information for all admissions, transfers, discharges, reasons and locations of admissions, discharges, and transfers, payment source and levels of care for all their residents.

  - Utilization by all Medicaid Certified NFs in Delaware of the Links to Payment tracking system on 100% of their residents, including those with Medicaid, those with any other payment sources, and those with PASRRs that pre-date the current data system.

DMMA seeks professional services to procure a web-based/vendor-hosted PASRR system that will enable the State to achieve regulatory compliance with federal Medicaid PASRR requirements codified in 42 CFR Subpart C 483.100-138, and that is compliant with State-approved browsers and servers.

The State wishes to solicit bids from experienced PASRR Contractors to operate the State of Delaware’s comprehensive PASRR process, which includes Level I screenings and Level II evaluations 24 hours per day, 365 days per year, for individuals who may seek admission to Medicaid-certified Nursing Facilities (NFs) in Delaware. The State wishes to partner with a vendor who demonstrates strong PASRR knowledge and understanding of CMS expectations for individuals with PASRR-related disabilities who seek admission to NFs. In addition to a web-based system, we are seeking qualified Mental Health and ID/DD service staff to perform Level 1.5 and clinical review and Level II PASRR independent evaluations that meet federal requirements. The PASRR program would also include a wide variety of performance and quality assurance activities, monitoring of compliance with care planning and service delivery of specialized services, collection and exchange of data with the State’s Medicaid payment system, tracking of NF admissions, transfers, and discharges, and development and delivery of PASRR-related training.

The schedule of Procurement Activities and due dates is below:

| Activity | Schedule |
| --- | --- |
| Public Notice | August 12, 2024 |
| Deadline for Questions | August 23, 2024 |
| Mandatory Pre-Bid Conference Call | August 26, 2024 @ 1 PM EST |
| Response to Questions | August 30, 2024 |
| Deadline for Receipt of Proposals | October 21, 2024 @ 1 PM EST |
| Estimated Notification of Award | December 9, 2024 |

# DHSS Program and System Overview

## DHSS

The following is an overview of the Department and Divisional structure of the organization within which DMMA is housed.

Department of Health and Social Services (DHSS)

The mission of DHSS is to improve the quality of life for Delaware's citizens by promoting health and well-being, fostering self-sufficiency, and protecting vulnerable populations.

DHSS is comprised of twelve Divisions as follows:

Division of Substance Abuse and Mental Health (DSAMH)

Division of Child Support Services

The Delaware Health Care Commission

Division of Health Care Quality

Division of Management Services

Division of Developmental Disabilities Services (DDDS)

Division of Public Health

Division of Services for Aging and Adults with Physical Disabilities

Division of Social Services

Division of Medicaid and Medical Assistance (DMMA)

Division of State Service Centers

Division for the Visually Impaired

## The Division

The Division (Ordering Agency)

The Division of Medicaid and Medical Services (DMMA) is Delaware’s Single State Medicaid agency. Its mission is to improve health outcomes by ensuring that the highest quality medical services are provided to the vulnerable populations of Delaware in the most cost-effective manner.

As of May  2024, approximately 270,838 members were eligible in Delaware’s Medicaid program. Approximately eighty percent (80%) of those eligible receive their services through the managed care plans under Delaware’s Diamond State Health Plan (DSHP), five percent (5%) receive their services through the State’s managed long-term services and supports program (Diamond State Health Plan Plus (DSHP-Plus)) and 15% receive their services through the State’s Medicaid fee-for-service program.

The State of Delaware Department of Health and Social Services, Division of Medicaid and Medical Assistance (DMMA) seeks professional services to procure a web-based Preadmission Screening and Resident Review (PASRR) system that will enable the State to achieve regulatory compliance with federal Medicaid PASRR requirements codified in 42 CFR Subpart C 483.100-138 and that is compliant with State approved browsers and servers. The State wishes to partner with a vendor who demonstrates strong PASRR knowledge and understanding of Centers for Medicare and Medicaid Services expectations for individuals with PASRR-related disabilities who seek admission to Nursing Facilities. In addition to a web-based system, we are seeking qualified Mental Health and intellectual disability service staff to perform Level 1.5 clinical review and Level II PASRR independent evaluations that meet federal requirements. We are also seeking a system that incorporates a service monitoring process for individuals with a need for PASRR-identified services in their PASRR Level II summary of findings as well as an ongoing quality management program for measuring and reporting performance. We seek a system that can link PASRR information to the Agency’s Medicaid payment system as well as an on-going quality management program for measuring and reporting performance.

DMMA, DSAMH & DDDS will utilize the system and share in the cost.

The DSAMH’s services and programs include the Delaware Psychiatric Center (DPC); Crisis Intervention Services (CIS); Prevention Services; standards for Service Providers for various treatments and certifications; the Treatment Access Center (TASC) a liaison with the criminal justice treatment agency systems; and Substance Abuse Help by providing public drug and alcohol treatment services for adults.   DDDS supports individuals with intellectual and developmental disabilities by working to identify and support the unique needs of eligible service recipients.  This includes access to employment and pre-vocation services; support coordination and community navigation; assistive technologies; respite; day and residential programs and options for supported living.

The three groups responsible for the development and operation of the automated systems that support the Division are described below. These three groups will be responsible for review and approval of all project deliverables, invoices and milestone payments. Information Resource Management (IRM) will serve as the liaison with the Department of Technology and Information (DTI) (see below). The selected Contractor will coordinate efforts for this project with the Project Director, other project Contractors, State of Delaware participants, and stakeholders.

### Information Resource Management (IRM)

The Project Director will oversee the project budget in coordination with the Department of Technology and Information (DTI), State Office of Management and Budget (OMB), and the Division.  The IRM unit is responsible for providing DHSS Divisions with direct programming support of automated systems, as well as consulting support and management of automated systems software, Contractors and development projects. IRM consists of an Applications Development, Technology Planning, Base Technology, Telecommunications, Security, and Help Desk support group all who participate in all phases of the project lifecycle, as appropriate.

IRM will appoint a Project Director with broad oversight authority for all project activities. A Technical Manager will be appointed and report to the Project Director for project-related activities. The Contractor on this project will report to the Project Director. The Project Director will report to the Director of IRM and have a dotted line to DTI’s Director of Major Projects.

### Department of Technology and Information (DTI)

DTI is a separate cabinet-level agency responsible for running the majority of other State agencies’ computer operations, the wide area data network, and setting and enforcing Statewide IT policy and standards. DTI as a separate State agency does not fall under the authority of DHSS. However, the Project Director has a dotted line to DTI’s Director of Major Projects and is required to work with DTI groups throughout all phases of the project lifecycle, review project deliverables, and oversee the project budget.  DTI is responsible for supplying Wide Area Network (WAN) systems support to DHSS as well as other State agencies. DTI also provides State agencies with technical consultant services.

### Division Business Analyst Group

This group serves as the Division liaison between IRM and Contractor technical staff with program staff. They typically translate business needs into IT requirements and vice versa. This is a critical function that ensures that Division business requirements are properly communicated to technical staff and that Division program staff understand IT policies and standards as they relate to the project. This group works closely with IRM and Contractor staff on all technical aspects of the project to ensure close communication with program staff on all phases of the project life cycle including RFP, business case process, Contractor negotiations, deliverable review and signoff, through testing, implementation, and post-implementation support. For this project, a Functional Manager will be appointed. This position will report to the Project Director for project-related activities.

# DHSS Responsibilities

The following are DHSS responsibilities under this RFP.  Outlined in the following subsections are such areas as project staffing, project management, available resources, and system testing and implementation (if applicable). DHSS staff expectations for this initiative beyond what is stated here must be clearly spelled out by the Contractor.

## Staffing Roles

As stated above, the Division will appoint a Project Director. The Project Director will serve to manage project staff including Contractor staff during this project. All project deliverables will be approved by signature of the Project Director, Technical Manager and the Functional Manager. The Project Director will serve as the overall project lead with input from the Technical Manager and the Functional Manager

The Project Director will serve as primary coordinator to ensure that Joint Application Design (JAD) sessions take place with the appropriate subject matter experts (SME), that project documents and deliverables are thoroughly reviewed, and that approval takes place within agreed upon timeframes. This individual is also responsible for scheduling and coordinating User Acceptance Testing (UAT), when appropriate.  The Project Director will coordinate with other Divisions and State agencies for their input as needed. These staff will serve primarily as subject matter experts on relevant Division applications and related systems and will participate in meetings and deliverable review as necessary.

The Technical Manager and the Functional Manager will serve as primary technical liaisons to ensure that Contractor and DHSS and DTI technical staff work together effectively to identify current and future technology considerations and make key technology decisions. The Technical Manager will serve as the primary liaison with DTI staff to gather State level input as needed.

The Project Director will report to a Project Steering Committee made up of representative managers from the Division, IRM and DTI. This Committee will meet monthly to review project status, progress and issues. The Project Steering Committee will report to an Executive Sponsors group. The Executive Sponsors group will be made up of representatives from DHSS, DTI, OMB and the Division. They will meet quarterly to discuss overall project status, progress and issues, project management, funding, staffing, sponsor issues, stakeholder participation and tasks planned for the upcoming quarter.

### Project Organization Chart

The following organization chart outlines the proposed management structure for this

project.

## DHSS Staff Participation

The Project Director will be assigned to work on this project full time. Additional DHSS staff participation is as assigned and is in addition to their primary responsibilities. DHSS staff normally work 7.5-hour days from 8:00 AM – 4:30 PM, although some staff flex their schedules. No DHSS staff will be available for data cleanup or meta-data definition.    However, Divisional SME’s can serve to advise Contractor on these topics. No DHSS technical staff will be assigned to this project to assist in the coding of the system. DHSS technical staff will attend JAD sessions as assigned. It is important to note that documentation on the existing systems may be missing, incomplete, out of date or in error. Division staff will be responsible for user acceptance testing. The Division will be responsible for assigning a primary and backup Division liaison and knowledgeable subject matter experts for the duration of JAD sessions related to their areas of expertise. These assignments will be sent to the Project Director prior to the start of the JAD sessions. Attendance at these sessions is mandatory for assigned staff. These same subject matter experts along with other staff will be assigned to participate during UAT for their areas of expertise. Adequate Divisional staff participation is critical.

## Resource Availability

IRM applications, telecommunications and Helpdesk staff are on site from 8:00 AM to 4:30 PM on State business days. The State network is very stable and unscheduled downtime is minimal. Given that the network is an essential State resource, any reported problems have a very high priority and are dealt with immediately. Biggs Data Center power is air-conditioned and outside supply fluctuations can trigger a switch to automatic local power generation capability. DHSS has audio and video-conferencing capabilities as well in specific on-site locations for remote meeting participation. Remote connectivity through SSL-VPN is available for offsite work for contracted staff that must access, update or maintain servers and/or applications in the DMZ. Please refer to Exhibit C for more information on the DHSS IT environment.

## Change Control

Scope control is critical to the success of any IT project. If the project is to remain on time and within budget, scope must be tightly managed. In this vein, the project will establish a Change Control Board (CCB) to review all changes requested beyond the scope established in the contract. This entity will be made of representatives from DHSS (Business and IRM) and the project Contractor(s) to review Change Requests (CRs) and vet them as to whether they are critical for inclusion in the implemented solution. Non-critical requests will be prioritized for consideration in the M&O phase. CRs may be swapped for CRs of similar level of effort in order to contain scope.  At a certain point, however, design must be locked down at which point no other CRs will be considered for inclusion at implementation. This design lock down date must be documented in the baselined project plan deliverable. The change control process will be documented in the Communications Plan deliverable.

## Deliverable Review

It is the responsibility of DHSS to perform deliverable review including User Acceptance Testing on all functional aspects of the project. DTI may participate in the review process for certain deliverables. It is the responsibility of DHSS to review all project deliverables in the agreed upon timeframe. DHSS will notify the Contractor of any changes to the review schedule. Milestone invoicing and payment is contingent upon formal DHSS approval. Likewise, production implementation of each module is contingent upon formal DHSS approval.

## Implementation

Production implementation is normally an IRM responsibility.  Depending on the solution selected, IRM may require participation of Contractor staff.  DHSS will be primarily responsible for post implementation administration if the system resides at the Biggs Data Center. If a hosted solution is selected, the Contractor has primary administration responsibilities.

# Contractor Responsibilities/Project Requirements

The following are Contractor responsibilities and project requirements under this RFP. Please note that specific roles, responsibilities and expectations for DHSS staff under this initiative should be delineated in Section 3.

The Contractor is expected to provide most of the expertise and provide for the full range of services during the project. Contractors must discuss each of these subsection requirements in detail in their proposals to acknowledge their responsibilities under this RFP.

Contractors must have demonstrated experience and depth in the following areas:

- The Contractor shall have experience in the design, implementation, and management of a web-based PASRR system that meets the State’s regulatory obligations. The following are the Core PASRR Components:

- Describe how the system provides Level I screeners with an efficient and

consistent method of completing and submitting Level I screening tools. Include a description of how the Level I tool meets or exceeds CMS/PASRR Technical Assistance Center design principles and data elements outlined in the 2015 PASRR National Report, Section 2 (see Exhibit M).

- Compliance with Federal PASRR expectations regarding Level I screening outcomes. The system screens out all individuals who clearly have no indicators of PASRR conditions and screens in for further Clinical Review all individuals with potential PASRR disabilities.

- Describe how the system is sensitive to potential PASRR qualifying     conditions and prioritizes triggered screens for immediate clinical review.

- Include a quality review process of:

a. Level I - screening

b. Level 1.5 – assessment review

c. Level II - evaluation

- Describe how the system assures expedient clinical review of triggered Level I screens to avoid unnecessary delays in hospital discharge and Nursing Facility (NF) admission. Include average time frames. Responsiveness of system should demonstrate expediency of response time for completion of Level I and Level II results in hours/days.

- Explain how the system will provide real-time Level I decisions regarding the need for further Level II activity and if applicable, meets categorical, exemption, exclusion, or full Level II evaluation decisions.

- Describe workflow and clinical confirmation capabilities for Exclusions,

Exemptions, and Categorical decisions including issuance of findings and

tracking of time limited length of stay approvals.

- Describe how the Independent Evaluators understand the basis for any PASRR determinations by category.  Describe how the Independent Evaluator uses the PASRR system to input data; and to review documentation in the PASRR system to support the determination.  (See Exhibit N). https://dhss.delaware.gov/dhss/dmma/state_plan.html

- Describe how the system has workflow capability to refer full Level II screens to the Independent Psychiatric Consultant (IPC) for evaluation.

- Describe how the system will provide immediate access to Level I screening results to relevant State staff and end users.

- Describe how the system will include web-based submission of Delaware’s Nursing Facility (NF) Level of Care criteria items.

- Ability for Level I Screeners and State/Respondent staff to electronically

communicate individual case information during the Level I process, including the ability to upload supporting documentation of potential PASRR qualifying conditions.

- Describe how the system will provide an alternative submission solution, such as fax submission, when the web-based system is unavailable or in special cases the functionality to allow staff to put the cases “on hold”.

- Functionality for tracking of all dates of when a case is touched from submission of Level I through completion.

- Designate roles of the Level I screeners for accessibility to various reports and cases.  Functionality for State staff to access on demand reports regarding referral source, number, and results of Level I screens.

- Describe how the system provides an efficient and consistent method completing and submitting Level II evaluations that meet or exceed CMS/PASRR.

- Technical Assistance Center data elements and requirements outlined in Review of State PASRR Policies and Procedures, 6/12/2012 (See Exhibit O).

- Level II evaluation tool meets or exceeds CMS/ Payment Model Technical

Advisory Committee requirements, incorporates State Nursing Facility medical necessity criteria (See Exhibit P), and includes the State of Delaware Categorical Group Determinations.

- Recruit, vet, and provide ongoing quality oversight of Level II evaluators. Minimum evaluator requirements include a Registered Nurse (RN) with two (2) years psychiatric experience or a Licensed Clinical Social Worker (LCSW) with 1-year medical experience and 2-year psychiatric experience. However, there may be different requirements for Level II evaluators for each Division. The provider will work with each Division to ensure that each Division’s credential requirements are met. For example, Full Level II evaluations and Preliminary Summary of Finding reports may be conducted by provider’s clinical staff (Psychologist, Psychiatrist, Psychiatric Nurse Practitioner, or an RN with 2 years psychiatric experience), but in some cases, a Division may not allow an RN with 2 years. Therefore, the provider must be aware of such cases and provide the correct staff to complete work. In addition, the provider must be alert to the clinical complexity and geographical location to ensure quality and maximize affordability for volume required.

- The following are the minimum evaluator requirements to perform Level II comprehensive evaluations for Mental Health, ID/DD or RC assessments.    In addition, for assessments for Duals, the Level II Independent Evaluator must meet the requirements for both mental health and ID/DD or RC.

- Registered Nurse with 2 years psychiatric experience or a licensed clinical social worker with 1-year medical experience and 2-years psychiatric experience.

- Minimum evaluator requirements to perform Level II comprehensive evaluations for ID/DD or RC and duals with ID/DD or RC a Registered Nurse with 2 years ID/DD experience or a licensed clinical social worker with 1-year medical experience and 2 years ID/DD experience.

- Resumes, qualifications, and any conflict-of-interest concerns will be reviewed and approved by the agency.

- Will provide IPC evaluations and preliminary summary of findings to be approved and/or amended by Division of Developmental Disabilities Services and/or Division of Substance and Mental Health (DDDS/DSAMH) authority and these evaluations and preliminary summaries must be available in the system within 5 days from the time of Level II referral.

- Level II Independent Evaluators must be available to participate in State Fair Hearings.

- Describe reports that would monitor the effectiveness of the program and the frequency which reports would be available.

- Describe process in which Level Is and Level IIs will be held accountable for work performed based on the contract and steps to be taken upon missed Service Level Agreements (SLA)s. The selected vendor will be required through the contract to oversee/monitor evaluators who may have contracts with the State through a vendor such as DXC Technology.

- Reconsideration and Appeal Process

The Contractor shall be responsible for collaborating with DMMA in the Reconsideration and Appeal processes to facilitate DMMA’s comprehensive PASRR process.  The Contractor’s obligations include, but are not limited to, the following:

- Perform Reconsiderations in accordance with DMMA policy upon appropriate written request by an individual who may access the Reconsideration process within ten days following the PASRR determination.

- Complete the Reconsideration determination within an average of five calendar days from receipt of a verified written request for Reconsideration with all information necessary to complete the Reconsideration.

- Participate in all aspects of preparation for appeals including downloading documents from the DMMA Appeals System, responding within specified timeframes, storing all appeals related documents within an identified Appeal or Reconsideration section of the database, timely preparation of appeal summaries, participate in pre-hearing teleconferences or meetings as needed, providing expert testimony from appropriate staff including Level II assessors and participate in State Fair Hearings as required by the DMMA. DMMA Fair Hearing Decisions - Delaware Health and Social Services - State of Delaware

- Attend and represent the PASRR process and DMMA in hearings with Administrative Law Judges as requested or required by DMMA in accordance with timeframes specified by DMMA.

- Require staff with involvement in the determination under appeal to testify if it is determined by DMMA that their testimony is needed.

- Provide training to the Delaware PASRR staff to prepare them to give testimony in a professional manner using guidelines for appropriate testimony.

- PASRR Care Planning and Services Monitoring Process including Identified Specialized Services (SS)

A services monitoring process for individuals with a need for PASRR Identified Specialized Services (SS) in their Level II Summary of Findings.  This monitoring process includes:

- A web-based system for requesting care plans and documents that support and verify that SS are being delivered.

- Reviews are triggered on 100% of individuals for whom SS are identified in their PASRR.

- Ability of the Nursing Facilities to receive an electronic notification when their PASRR compliant care plans are due and ability for NFs to upload their documents, including proof of delivery of SS and any other services if/when requested.

- Contractor- led review, reporting, and technical assistance regarding care planning, proof of delivery of SS, PASRR identified service delivery, transition planning, and other compliance issues discoverable during the process of review.

- Include in this process identifying and reporting on all compliance issues discovered during the full review, including but not limited to days of preadmission non-compliance, gaps in days between PASRR approvals, apparent time frames for non-compliance with care planning and service delivery, and failure to submit new screens when a status change has likely occurred.

- Contractor shall report to DMMA all situations where full compliance with care planning, service delivery expectations, or other identified compliance concerns are not achieved after two reviews and after technical assistance was provided.

The Contractor shall be responsible for care planning and a services monitoring process to facilitate the State of Delaware’s comprehensive PASRR process.  The Contractor’s obligations include, but are not limited to, the following.  The Contractor shall:

- Utilize a services monitoring process that is respectful of provider burden for completion of each review. The process shall require limited provider data entry while focusing primarily on provision/uploading of a compliant care plan and evidence that Specialized Services are being delivered, other PASRR identified services are adequate, and any other compliance issues are being addressed.  The process triggers a review for 100% of individuals for whom one or more SS are identified in their PASRR.

- Offer a second full two-step review when compliance is not achieved upon the conclusion of a first review.

- Send NF an electronic notification when their PASRR compliant care plans, proof of service delivery, and other documents are due, and permit NF to upload their care plans, proof of service delivery, and other documents.

- Conduct a thorough review, identify any other compliance issues that are discovered during the review process, provide in-depth technical assistance to the NF, review care planning and service delivery, resolve questions about where and how to find appropriate services, address how to document delivery of these within the facility care plan, and report outcomes to the facility and DMMA.

- Initiate electronic letters to the NF outlining the outcome of first, second, and any subsequent services reviews, generate outcomes electronically to the facility at the conclusion of each phase of the review process.  Each outcome letter will include language that the facility must include the review outcome in the individual’s PASRR record.

- Maintain a list of each PASRR resident by NF including details of SS, RS. The Contractor shall make the list available to DMMA upon request and as part of required reports.

- Report to DMMA any situations where full compliance with PASRR care planning and service delivery are not achieved after two reviews and provision of technical assistance.

- Data Exchange with DMMA Medicaid Managed Care Organizations (MCO’s)

If required, the Contractor shall be responsible for collaboration with DMMA or DMMA’s designee to facilitate the exchange of data to the Medicaid Managed Care Organizations - MCOs.  DMMA Medical Assistance Services: Medicaid - Delaware Health and Social Services - State of Delaware  The Contractor’s obligations shall include, but are not limited to, the following. The Contractor shall:

- Collaborate with the Agency or Agency’s designee in a process that involves matching PASRR information to Medicaid member/MCO data.

- Receive a data file from the Agency or Agency’s designee monthly, using a secure file transfer process that provides a tilde delimited text file formatted based on the Attachment J file layout specification.

- Perform a data match that compares the Agency file to the PASRR database and returns the matched data to the Agency or Agency’s designee, using a secure file transfer process that provides a tilde delimited text file formatted based on the Attachment K file layout specification.

- Prepare and deliver PASRR related training to the staff of the MCOs upon request of the Agency.

- Quality Management Program (QMP)

The Contractor shall be responsible for Links to Payment in the Delaware Medicaid Enterprise System (DMES) and quality assurance activities to facilitate the State of Delaware’s comprehensive PASRR process.  The Contractor’s obligations include but are not limited to the following:

- Provide a system where NF’s can report changes electronically such as admissions, transfers, discharges, and deceased residents. Also, provide NF’s mechanisms to report admission of Level II applicants, immediate access for viewing, downloading and printing of PASRR notices, outcomes and summaries of findings. Provide DMMA the ability to track and report as federally mandated the current NF placement of all residents with PASRR conditions identified through the level II process.

- Utilize the PASRR dates, as well as admission, transfer and discharge data entered by the NFs to track, identify, and monitor and report specific preadmission and other PASRR compliance issues and the location of all NF residents in all NFs throughout the state.

- Implement a quality assurance program to confirm whether NF are following all aspects of the PASRR process.  Collect data pertaining to any non-compliance discovered and report all data pertaining to compliance to the Agency per the schedule agreed upon by agency

- Provide functionality to streamline payment authorization for approved NF stays in Delaware linking the state’s Medicaid payment to the PASRR web-based system which may include nut not limited to secure data file transfer. Disallowing payment for any days of NF service that occurred prior to PASRR approval for admission or continued stay through an automated interface of Level I and Level II outcomes and dates to state payment authorization systems which may include exchange of such data to the state’s Managed Care Organizations.

- The Contractor will implement and operate an on-going quality management program at no additional cost to DHSS for measuring and reporting performance.  Corrective action plans will be documented and implemented.

- The Contractor will implement a Performance Monitoring System at no additional cost to provide DHSS an automated method and other tools used to provide reporting of the quality and performance measurements agreed upon by DHSS and the Vendor.

- DMMA will specify standard performance measurement reports to be prepared by the Vendors Quality Management Program (QMP) and Performance Monitoring System including an online dashboard displaying metrics as defined by DHSS. The reports must be posted in a central location specified by DHSS with alerts as reports are updated or posted. DHSS must have access to the data repository. See Exhibit Q Performance and Quality Reporting.

- Security, Password and Log-On Capabilities

  - Username Enumeration - Application’s login functionality should return straightforward message as “Invalid Password” vs “User (username) does not exist”. The application may return a generic failed login message that differs slightly depending on whether a valid username and invalid password are supplied vs an invalid username, or the application may display single error message, but some other (potentially non-visible) aspect of the response’s content is different.

  - Multi-Factor Authentication – The application should use multi-factor authentication to authenticate privileged users to the system.

- Project Reporting Requirements

The following is a cadence and schedule for reporting and meetings between State staff and the Contractor as the project is designed, developed, implemented and during maintenance and operations.

  - Weekly and as needed conference calls conducted by the Contractors Project Manager to commence when the Contract is signed. Schedules for the calls will be mutually agreed upon by the State and Contractor.

  - The Contractor will be required to report any immediate suspicion of system breach of Protected Health Information.

  - Notice of periods for planned and emergency system maintenance and updates.

  - Notice of Contractor office closings for holiday or weather-related events.

  - The Contractor will provide reports that monitor the Independent Evaluator’s effectiveness at a frequency agreed upon.

## Staffing

Contractor will propose and supply resumes for the following key positions including:

- Project Director

- Project Manager

- Project Management Office (PMO) Managers/Leads (e.g., Change Control, Risk/Issue/Action Item, etc.)

- Business Analysts (Analytics/Reporting, Organizational Change Management)

- Training Specialist

- Certification Manager/Lead

- Senior Developers/Technical Analysts

- Database architect

- Database administration

- Data analytics and reporting

- Data governance

- Data privacy and security

- Data integration

The resumes will be for specific named individuals and will be in the format specified in Exhibit D. Other positions may be proposed at the Contractor’s discretion. One person may be proposed to fill more than one role.

On-Site Staffing Requirement

The following key Contractor staff are required to be on-site from time to time, as relevant to the PASRR project. The Contractor project manager and other key staff such as the Business Analyst(s) may be required to be on-site as needed at a designated location to be determined.

- Contractor Project Director

- Contractor Project Manager

We expect minimal in-person on-site requirements for this project from other staff.

In general, DMMA staff work remotely and only once a week or occasionally work in the office.

### Project Director Requirement

The Contractor Project Director is the individual who has direct authority over the Contractor Project Manager and will be the responsible party if issues arise that cannot be resolved with the Contractor Project Manager. The Contractor Project Director does not need to be on-site except for designated meetings or as requested. It is critical that a named Contractor Project Director with appropriate experience be proposed.

### Project Manager Requirement

- The Contractor Project Manager may periodically be on-site (see 4.1 Staffing for exceptions) and manages the project from the Contractor perspective and is the chief liaison for the DHSS Project Director. The Project Manager has authority to make the day-to-day project decisions from the Contractor firm perspective. This Contractor Project Manager is expected to host meetings with Division Subject Matter Experts (SME) to review Division business organization and functions along with the organization, functions and data of existing information systems relevant to this project. The Contractor Project Manager is expected to host other important meetings and to assign Contractor staff to those meetings as appropriate and provide an agenda for each meeting. Weekly on-site status meetings are required, as are monthly milestone meetings. Meeting minutes will be recorded by the Contractor and distributed by noon the day prior to the next meeting. Key decisions along with Closed, Active and Pending issues will be included in this document as well. In their proposals, Contractors must include a confirmation that their project manager will schedule status review meetings as described above. It is critical that a named Contractor Project Manager with prior project management experience be proposed.

- In their proposals, Contractors must include a confirmation that their Project Manager will schedule status review meetings as required above and that their Project Manager will provide written minutes of these meetings to the DHSS Project Director by noon the business day prior to the next meeting.

### Project Help Desk Staff Requirement

Contractor Help Desk expertise is critical to the success of the system. Staff proposed for this function do not need to be dedicated exclusively to this role. They may serve a primary role in addition to providing Help Desk coverage. Secondary Help Desk support must be identified in the resume of the staff member primarily bid for another function. Contractor must supply at least a primary and a backup Help Desk function during the UAT, production implementation and the warranty timeframe. These staff will provide second-level support during DHSS business hours to callers with system issues. This will be more system-specific and require application expertise. The DHSS Help Desk will provide first-level support. This generally includes resolution of issues such as network connectivity, application log in problems and general PC advice. Specific system issues may be referred to third-level Divisional support for SME expertise.

## Project Management

The Contractor must be the prime Contractor to develop all the deliverables required by this RFP. The prime Contractor will be directly responsible for all project work and performance of any subsidiary, subcontractor or by any other third party. The prime Contractor will ensure that all ancillary Contractors understand and are responsible for the requirements of this project. If the prime Contractor will be utilizing the services of an ancillary Contractor under this project, please give an example of language to be used in the sub-contractual agreement to satisfy this requirement.

The Contractor must recommend a core team to work with DHSS over the course of the project and must identify other resources needed. A high-level draft baseline project plan must be created and included as part of this proposal.

For custom development, the Contractor is expected to employ a rapid application design methodology to speed customization/development.  An iterative model of testing is required which will require early prototypes and subsequent demonstrations of working modules to ensure that the product meets user specifications in terms of user interface and functionality. It will be the Contractor’s responsibility to provide complete and accurate documentation for all entities in the system. The Contractor is expected to release prototypes/drafts of project deliverables and components for early DHSS consideration and comment in order to expedite the final review process.

## Requirement to Comply with HIPAA Regulations and Standards

The selected Contractor must certify compliance with Health Insurance Portability and Accountability Act (HIPAA) regulations and requirements as described in Department of Health and Human Services, Office of the Secretary, 45 CFR Parts 160, 162 and 164 along with the updated ARRA and HITECH act provisions, as well as all HIPAA requirements related to privacy, security, transaction code sets (where applicable) and medical provider enumeration. The proposed solution must meet these cited requirements.

HIPAA requirements also apply to entities with which DHSS data is shared. If this data is covered by HIPAA, then the State Business Associate Agreement (BAA) must be signed by both parties to ensure that this data is adequately secured according to State policies and standards (See Section 4.4 for more information on this requirement). This agreement/contract must be in force prior to testing or production implementation of this data exchange. The signed BAA will be attached to the contract. Microsoft Word - Template,BAA 06.13.2023.dotx (delaware.gov)

If the Contractor signs the State BAA, subcontractors will not be required to sign the State BAA.

If the Contractor is a Covered Entity, they will not be required to sign the State BAA. However, in this case, subcontractors will be required to sign a BAA with the Contractor and this document will be attached to the contract. Additionally, if the Contractor does not sign the State BAA, the following language must be added to the contract:

Contractor shall perform for Delaware the services specified in the Appendices to this Agreement, attached hereto and made a part hereof. The parties will perform services that involve the use or disclosure of Protected Health Information (“PHI”)  that is subject to  the final federal  Privacy,  Security,  Breach  Notification  and Enforcement Rules (collectively the “HIPAA Rules”) issued pursuant to the Health Insurance Portability and Accountability Act of 1996 (the Act including the HIPAA Rules shall be referred to as “HIPAA”) and the Health Information Technology for Economic and Clinical Health Act of 2009 (“HITECH”), as each is amended from time to time. As such, each party represents that it shall comply with HIPAA in performance of the services.

In the proposal, Contractor will explain their understanding of the HIPAA regulations and their impact on this project especially in the area of security.

The Contractor shall demonstrate the following:

1. Creating and maintaining a secure user system providing HIPAA

compliant PASRR Level I and Level II system processes 24/7/365.

2. Pre-Qualify users as legitimate subjects prior to initial system access.

3. Provide re-qualification of end users on a scheduled basis.

4. Manage screening and provisioning of user credentials and system

access.

5. Describe how end users will be able to cover other users’ cases during

periods of absences.

6. Enter into a HIPAA business associate agreement with DMMA.

7. Follow DHSS/IRM/DTI Security policies and regulations (Exhibit C)

## Security Requirements

### Authorizations

All Contractor staff working under this contract will be subject to a Criminal Background Check (CBC). The Contractor will be solely responsible for the cost of the CBC. DHSS will review the CBC results. At their sole discretion, DHSS may request that a Contractor staff member be replaced if their CBC result is unsatisfactory. See Exhibit K for instructions on this process.

Contractor staff will be required to fill out DTI’s Acceptable Use Policy, Biggs Data Center User Authorization Form, and the Biggs Data Center Non-Disclosure Agreement for necessary authorizations before starting work under the contract. Staff working at a secured DHSS site will be issued a security access card by DHSS.

### Architecture Requirements

Securing and protecting data is critical to DHSS. This protection is required for data whether hosted onsite or offsite. As such it is required that the Contractor include in the response to this section proposed architectural diagram(s) in Visio format demonstrating how DHSS data is being secured.

The diagram must include any interfaces between the solution and other solutions. The diagram needs to be clearly documented (ports, protocols, direction of communication). It does not need to contain the inner workings of the solution or proprietary information.

Technical documentation will be required to be produced as part of the contract negotiations process. These will be submitted to DHSS for attachment to a DTI business case. The business case must be in “Recommended” status prior to contract signature or have a clear indication that the contract can be signed subject to conditions listed in the business case. The project business case is a DHSS responsibility. Technical documentation includes a final architecture diagram for each system environment (Prod, UAT, etc.), non-proprietary data dictionary and a high-level process flow diagram. This documentation shall be produced at no cost to DHSS prior to contract signature.

Architecture changes can be highly risky if not planned and tested correctly and therefore must go through the change control process. The architecture diagram may have to be updated along with other documents for prior approval.  Architecture changes must be staged in lower environments.at least at the Systems Integrator Testing (SIT) level for integration testing. Formal UAT approval is required for scheduling production implementation.

### DHSS Hosting Requirements

This section is only applicable if the solution is being hosted within the State network.

### Requirement to Comply with State Policies and Procedures

The proposed solution must be fully compatible with the DHSS technical environment. Proposed solutions that are not fully compliant with State standards may be disallowed.

The Information Technology Publications web page (The link to this document is in Exhibit C.) has links to DHSS and DTI policies and standards and other documentation. See the “Supportive Documentation for Bidding on Proposals” section.

- Please review the MCI and IAS documents referenced on this page. MCI is the Master Client Index which is required for all systems identifying DHSS clients. IAS is the Integrated Authorization System which is a DHSS mechanism for tracking authorized systems users. Contractors will comply specifically with these requirements.

The DTI Systems Architecture Standard contains information confidential to the State and is not published on the internet. However, DTI has set up an email address which will automatically send a response with this document attached. The email address is sysarch@lists.state.de.us.

The application will have at least 3 tiers with the tiers configured and secured as in the sample diagram included in the DHSS Information Technology Environment Standards.  Please see State of Delaware Systems Architecture Standard (The link to this document is in Exhibit C.) and DHSS Information Technology Environment Standards (The link to this document is in Exhibit C.) for more information.

All components of the proposed solution, including third party software and hardware, are required to adhere to the policies and standards described above, as modified from time to time during the term of the contract resulting from this RFP, including any links or documents found at the above referenced web sites.

### Standard Practices

The Contractor(s) shall be responsible for the professional quality, technical accuracy, timely completion, and coordination of all services furnished to DHSS.  The Contractor(s) shall follow practices consistent with generally accepted professional and technical policies and standards. The Contractor(s) shall be responsible for ensuring that all services, products and deliverables furnished to DHSS are consistent with practices utilized by, or policies and standards promulgated by, the Department of Technology and Information (DTI). The link to the Enterprise Standards and Policies is in Exhibit C. If any service, product or deliverable furnished by a Contractor(s) does not conform to State policies, standards or general practices, the Contractor(s) shall, at its expense and option either (1) replace it with a conforming equivalent or (2) modify it to conform to State policies, standards or practices.

### Confidentiality and Data Integrity

The Department of Technology and Information is responsible for safeguarding the confidentiality and integrity of data in State computer files regardless of the source of those data or medium on which they are stored, e.g., electronic data, computer output microfilm (COM), tape, or disk. Computer programs developed to process State Agency data will not be modified without the knowledge and written authorization of the Department of Technology and Information. All data generated from the original source data, shall be the property of the State of Delaware.  The control of the disclosure of this data shall be retained by the State of Delaware and the Department of Technology and Information.

### Security Controls

As computer, network, and information security are of paramount concern, the State wants to ensure that computer/network hardware and software do not compromise the security of its IT infrastructure. Therefore, the Contractor is guaranteeing that any systems or software meets or exceeds Critical Security Controls. The link to this document is in Exhibit C.

### Cyber Security Liability

It shall be the duty of the Contractor to assure that all products of its effort do not cause, directly or indirectly, any unauthorized acquisition of data that compromises the security, confidentiality, or integrity of information maintained by the State of Delaware. Contractor’s agreement shall not limit or modify liability for information security breaches, and Contractor shall indemnify and hold harmless the State, its agents and employees, from any and all liability, suits, actions or claims, together with all reasonable costs and expenses (including attorneys' fees) arising out of such breaches. In addition to all rights and remedies available to it in law or in equity, the State shall subtract from any payment made to Contractor all damages, costs and expenses caused by such information security breaches that have not been previously paid to Contractor.

### Information Security

Multifunction peripherals must be hardened when used or connected to the network. They should be configured to harden the network protocols used, management services, processing services (print, copy, fax, and scan), logging, and physical security. Care shall be taken to ensure that any State non-public data is removed from memory before service calls and/or equipment disposal. Electronic information storage devices (hard drives, tapes, diskettes, compact disks, USB, multifunction peripherals, etc.) shall be disposed of in a manner corresponding to the classification of the stored information, up to and including physical destruction.

### Mandatory Inclusions

### Network Diagram

The Contractor must include a network diagram of the user’s interaction with the solution and any interfaces between the solution and DHSS must be clearly documented (ports, protocols, direction of communication).  The network diagram does not need to contain the inner workings of the solution or proprietary information.

### List of Software

The Contractor must include a list of software (operating system, web servers, databases, etc.) that the State needs to utilize the solution.  For example, a certain web browser (IE) or web service technology for an interface. The Contractor will include a list of browsers and versions that are officially supported for web applications. Please use the following format:

| Product Name | Version | Contractor Name | Required for Development? | Required for M&O? |
| --- | --- | --- | --- | --- |

### 3rd Party Authentication

The Contractor must include a list of any 3rd party authentication solutions or protocols that they support.

### Password Hashing

The Contractor must describe the method used by the solution for hashing user passwords.  Include items like hash algorithm, salt generation and storage and number of iterations.

### Data Encryption

The Contractor must describe the solution’s ability to encrypt non-public State data in transit and at rest. Include encryption algorithm(s) and the approach to key management.

### Securing DHSS Data

The Contractor must describe how DHSS data will be protected and secured.

### Mandatory Inclusions for Cloud/Remote Hosting

This section is only applicable if the data and/or service is not being hosted within the State network.

### Network Diagram

The Contractor must include a network diagram of the user’s interaction with the solution and any interfaces between the solution and the State needs to be clearly documented (ports, protocols, direction of communication).  The network diagram does not need to contain the inner workings of the solution or proprietary information.

### List of Software

The Contractor must include a list of software (operating system, web servers, databases, etc.) that the State needs to utilize the solution.  For example, a certain web browser (IE) or web service technology for an interface. The Contractor will include a list of browsers and versions that are officially supported for web applications. The software list will be formatted as follows:

| Product Name | Version | Contractor Name | Required for Development? | Required for M&O? |
| --- | --- | --- | --- | --- |

### DTI’s Terms and Conditions Agreement

DTI’s Terms and Conditions Governing Cloud Services and Data Usage Agreement (“T&Cs Agreement”) must be signed for provision of XaaS and accessing/storing State data outside of the State network. This document has columns identifying which provisions are mandatory depending on whether the data is Public or Non-Public.

The data classification for this procurement is Non-Public.

The mandatory clauses are identified by the checkmark in the appropriate Public/Non- Public column in the T&Cs Agreement. Contractor is instructed to review this document and sign and scan as applicable and include with your response.

Paragraph 5 specifies that State PII and/confidential information must be encrypted at rest. If the Contractor is proposing a solution that will comply with this requirement, please include the following statement in your response to this section:

- “[Contractor Name] is proposing a solution encrypting State PII at rest.”

In section 4.4.8.1 of this RFP, Contractor must specifically describe how the data will be encrypted at rest.

Cyber Liability Insurance

If the Contractor cannot comply with the requirement to encrypt State PII and confidential data at rest, then Contractor must purchase adequate Cyber Liability Insurance as specified in paragraph 11 of the Agreement. Please include the following statement in your response to this section:

- “[Contractor Name] is proposing a solution that will not encrypt State PII and confidential data at rest and intends to purchase Cyber Liability Insurance at the proper level and provide a valid certificate prior to contract signature.”

The selected Contractor will present a valid certificate of Cyber Liability Insurance for attachment to the contract prior to contract signature. Terms and Conditions Governing Cloud Services and Data Usage Agreement (delaware.gov)

### Agreement Exceptions

If Contractor can only accept a clause with conditions (Accept Conditionally) or does not agree with (Reject) a clause as written, then please fill out the following DTI T&Cs Agreement Exceptions table as part of your response to this section. Please include a Comment for each exception stating why you Accept Conditionally or Reject. If you Accept Conditionally, state what controls are or can be put into place to provide for the same or similar level of compliance.

DTI T&Cs Agreement Exceptions (Example)

| Paragraph | Response | Comment |
| --- | --- | --- |
| 5 | Accept Conditionally | We cannot encrypt data at rest. However, we intend to substantially comply with the Cyber Liability Insurance requirement. |
| 7 | Accept Conditionally | We will provide the results of our internal Criminal Background Checks in lieu of the stated requirement. |

Any exceptions specified will be vetted by DTI prior to contract signature. Individual clauses may be negotiated and updated by DTI. In this case, DTI’s written approval of the negotiated Agreement version will be attached to the final contract.

If the Contractor accepts all clauses as originally specified, Contractor will respond to this subsection with “We accept all clauses in the T&Cs Agreement”. Do not include the Template Exceptions table in this situation.

### Subcontractor Requirements

Subcontractors are not required to sign the T&Cs Agreement; however, the Contractor is expected to hold them responsible to the same or more stringent security requirements to ensure that State data is adequately secured.

The Subcontractor Information Form is included as Attachment 6 in the RFP and must be filled out by the Contractor and signed and dated by both the Contractor and Subcontractor. This form will be required for a change in or addition of subcontractors and attached to a contract amendment after contract signature.

### Standard Practices

The Contractor(s) shall be responsible for the professional quality, technical accuracy, timely completion, and coordination of all services furnished to DHSS.  The Contractor(s) shall follow practices consistent with generally accepted professional and technical policies and standards.

### Additional Security Requirements

### Encryption of Data at Rest

If Contractor intends to encrypt State PII/confidential data at rest, please describe the method(s) for encrypting this data.

### Encryption of Data in Transit

All State data in transit must be encrypted whether transmitted over a public or private network. Contractor will describe the encryption method(s) proposed.

### DHSS Data Rights

All State data (Public and Non-Public) related to services provided under this contract will remain the sole property of the State. De-identified or derived/aggregated State data is not exempted from this requirement. This provision shall survive the life of the contract. Contractor does not acquire any right, title or interest in State data under this contract. Except as otherwise required by law or authorized by the State in writing, no State data shall be retained by the Contractor for more than 90 days following the date of contract termination. After the 90-day timeframe the following provisions will remain in effect: Contractor will immediately delete or destroy this data in accordance with NIST standards and provide written confirmation to the State; Contractor is expressly prohibited from retaining, transferring, repurposing or reselling State data except as otherwise authorized by the State in writing; Contractor retains no ongoing rights to this data except as expressly agreed to by the State in the contract.

### UAT and Training Environments

The UAT and Training environments must be secured at a level equivalent to the security in place for the production environment. It must be sized and architected such that production-sized files can be copied over into UAT. The architecture must be equivalently configured so that performance and load testing will essentially produce the same results and expectations as testing in the production environment. Depending on the type of data (i.e. top secret/highly confidential, behavioral health) and specific security requirements around this data, there may or may not be an expectation to mask field values in the UAT and Training environments. Copying production data into lower environments may be prohibited especially for role-based training. Lower environments with production data that are secured in the same manner may be exempt from masking requirements as well however this may be subject to DHSS or Federal policies and regulations that override this potential exemption or explicitly disallow production data being copied into lower environments. The Division DAG will be consulted on what is allowed/disallowed in non-production environments.

### Masking of Production Data in Lower Environments

While securing of production data is of critical importance, migration of that data to lower environments presents its own set of challenges as lower environments typically are not as secure as the production environment. Masking of production data in lower environments usually involves deletion or obfuscation of actual PII-related field values such that they have no meaning as plain text and there is no identifiable method of translation back to the original values. If there are plans to copy production data to a less secure environment, Contractor will describe in detail their proposed masking strategy. If there is no expectation that production data will be copied into less secure environments, Contractor will describe their proposed test data generation plans and state clearly in this section that masking of production data is not required under this proposal.

### Offsite Project Work

DHSS will permit project work to be done offsite, within the United States and its territories. For offsite work, DHSS requires strong management of the resources and assigned tasks; adequate, timely and accurate communications and completion of assigned work by specified deadlines. This is important to any offsite relationship. If Contractor is proposing offsite project work, Contractor must specifically address each of the bulleted items below in this section of the proposal. Otherwise, Contractor will respond to this section as follows: “No offsite project work proposed.”

Note: For the purposes of this section, the Contractor staff organization includes subsidiary Contractors.

Provide a detailed description of work to be completed offsite along with a breakdown of the type of work to be provided on-site.  Quantify this by estimating for each of the deliverables identified in this Section, the percentage of work to be done offsite.

Provide an organization chart with job titles of offsite staff and their relationship to the Contractor.

Provide a description of what tasks each job title is responsible for performing.

Clearly identify if offsite work is to be performed by Contractor staff or subcontractors.

For offsite subcontractor or Contractor staff, please include the names and resumes of key staff, highlighting prior participation on similar projects. Also provide named or sample resumes for lower-level staff.

Provide a detailed plan for managing offsite work including communication strategy to accommodate time differences if any. Include contingency plan for completing work should offsite relationship be terminated.

Propose a meeting schedule for project status discussions with offsite management staff.

Identify the offsite single point of contact who will serve as the project manager of offsite resources.  Describe how this project manager and the on-site project manager will interact. DHSS prefers that the offsite project manager be a Contractor employee. Please refer to RFP Section 4.1 for normal Contractor staffing requirements.

Provide a contingency plan for substituting on-site staff if offsite relationship becomes problematic as determined by DHSS.

Provide a description of prior Contractor organization experience with use of offsite Contractor staff or subcontractors and provide U.S. client references for that work.

Provide a detailed description of proposed project manager's experience in directing offsite staff and/or subcontractors.

Describe your understanding that DHSS will only provide management of this project and Contractor resources through the on-site project manager.  All management/relationships with offsite resources, whether Contractor staff or subcontractors, will be handled by the respective bidding organization.

Describe how the system components will be tested and staged during customization/development.  For DHSS-hosted solutions, DHSS requires that all UAT, production and related environments be located at the Biggs Data Center. All system components of these environments including all system libraries and databases will be located in the data center as well. DHSS staff must approve the results of system testing before systems components are migrated into UAT. It is critical that system components are proven to operate in the Biggs Data Center UAT environment prior to promoting the code to production. Remote developers and testing staff may access these environments through VPN. The UAT environment must be the technical equivalent of the production environment to minimize issues with promoted code and/or database changes in production. Contractors may propose additional environments as necessary or recommended for their solution.

### Offshore Prohibitions

See Offshore IT Staffing Policy in Exhibit C.

Offshore is defined as not being within the United States or its territories. Offshore storage and transmission of DHSS data is prohibited. Onshore project data and project artifacts including backup and recovery files in any form shall not be accessed by offshore staff and shall not be copied, processed, transmitted or moved offshore. Contractor is permitted to engage offshore resources including sub-Contractors for development and lower level (unit & integration) testing only. Contractor is prohibited from using State data in any form even if masked or obfuscated for offshore testing. All aspects of User Acceptance Testing and production operations will take place onshore.

The provisions in this section extend to development, maintenance & operations services, hosting services, technical support services and any other subsequent services under this contract. Violation of any provision in this section will be considered breach of contract. Contractor shall respond with their understanding of and their intent to comply with the requirements in this section.

### Other Technical Considerations

DHSS prefers to have a system with a web front-end for a common user interface.  Web browser-based applications are now considered the only acceptable platform for custom applications development. For proposed COTS (Commercial off the Shelf) solutions, DHSS prefers those that are web browser based and that:

- Use Microsoft Windows Server as their operating system

- Use Microsoft Internet Information Server (IIS) as their web and application server software

- Use Microsoft SQL Server for the data store

- Have been developed using Microsoft C#.NET

## Reporting

To the extent possible, reporting should utilize an extracted or near real time copy of the production database so as not to adversely affect the performance and response time of the production application. This is critically important for systems that permit ad-hoc reporting or user-constructed queries. DHSS encourages the use of a separate reporting environment especially for complex systems or systems with a large concurrent use base. If a separate reporting environment is being proposed, Contractors will include a corresponding system architecture diagram in their proposal.

## Performance

Performance of the proposed solution within DHSS and State technical environments is a critical consideration. The present data center environment in terms of infrastructure, hardware, power, etc. needs to be reviewed. The selected Contractor will be expected to review this with IRM and DTI to ensure that it is sufficient. The current design and capacity of the network especially in terms of connectivity to the Division business sites must be reviewed along with service upgrade plans. Future capacity and response time needs must be evaluated and accepted.

## Customizable COTS Solutions

If bidding a purely custom solution, please respond to this section as follows: “Bidding a custom solution. COTS customization limitations are N/A.”

COTS Customization in this regard is the application of new or custom features unique to this contract that are beyond the resident configuration functions of the system. This involves the development of new or modified code for this purpose.

DHSS’ interest is in prevention of scope creep by limiting customization features applied to a proposed COTS solution. In this vein, the DDI scope must be governed by the functional requirements and the system design documented in deliverables signed off by both parties. Suggested features and functions outside of this must follow the change control approval process. If they are approved, from a project control standpoint, their development should be moved to a separate phase of the project after the originally designed functionality has been successfully implemented.

Bidder will describe how they apply project controls towards the successful implementation of their COTS solution within time and budget constraints.

## Backup and Recovery

DHSS requires that system data be backed up to appropriate media that can be restored as necessary. The selected Contractor will be expected to review the current backup and recovery process and suggest scenarios where incremental backups, full backups or dataset reloads are appropriate.

## Disaster Recovery

Locally Hosted Systems

DHSS utilizes Cloud backup storage to contain production backups. DHSS has a vendor that provides a Cloud Disaster Recovery environment in the event of a prolonged outage locally. Disaster Recovery test are conducted periodically (at a minimum once a year) for the Biggs Data Center Environment. If the vendor/Contractor has ongoing maintenance responsibilities for a system, they will be required to participate to the extent necessary in any testing.

This requirement will be detailed in the maintenance agreement/contract and will also include expected turnaround time and recovery participation in the event of an actual disaster declaration.

Remotely Hosted Systems

For systems hosted offsite, bidders will describe at a high level their disaster recovery arrangements as it would apply to this contract, the frequency of recovery testing and expectations as far as DHSS staff participation in this testing. Documentation is also required from the bidder on a disaster recovery procedure/test and DR test results from each DR Exercise/Drill.

## Specific Project Tasks

Contractor will be expected to address the following requirements in their proposal in detail.  Emphasis is on the limited availability of DHSS staff for the project and the expectation that the Contractor expresses in detail their understanding of their responsibilities for each of these tasks. Contractor is expected to have primary responsibility for each of these project tasks. DHSS versus Contractor responsibilities must be delineated. See Exhibit L Certification Requirements and Exhibit Q Performance and Quality Reporting.

## Project Deliverables

### Deliverable Review Process

Contractor shall describe and host a SharePoint to be used throughout the project lifestyle for organization, sharing and storing of document deliverables.

Software deliverables will be delivered and installed by technical staff as agreed to by DHSS. DHSS staff time is limited on this project especially for deliverable review. The project plan must include sufficient time for serial deliverable review. The Contractor must include at least ten (10) business days, per deliverable, in the project plan for DHSS staff to complete a review and to document their findings. Based on the review findings, DHSS may grant approval, reject portions of, reject the entire deliverable or request that specific revisions be applied. DHSS may also request in writing a short extension to the review timeframe until a specified date. The Contractor shall have five (5) business days to revise the deliverable/cure identified defects as requested by DHSS. DHSS shall have three (3) business days for subsequent reviews as necessary. These review timeframes may be modified as necessary for a specific deliverable (i.e. complex deliverables may require greater review time) but must not adversely affect the critical path in the baseline project plan. Review timeframe modification requests must be made in writing by either DHSS or Contractor staff to the Project Director. These requests will be approved or rejected at the sole discretion of the Project Director.

For solutions hosted at the Biggs Data Center, specifically for each application module deliverable, the source code (or executable in the case of COTS products) will be delivered to DHSS. The Contractor is responsible for installation in the specified test environment with the assistance of DHSS technical staff. The Contractor is responsible for ensuring that each module deliverable can be tested by DHSS staff.

Deliverables will be reviewed by DHSS and will require formal approval from the Project Director, Technical Manager and Functional Manager prior to formal approval and invoicing. Formal approval of a deliverable constitutes DHSS approval of the final version. Deliverables will be accompanied by a Deliverable Acceptance Request (DAR) form – see Exhibit I. The goal for the deliverable review process is to complete the review in a maximum of two (2) cycles. However, review will need to extend beyond the second cycle if a deliverable still has defects.

- In the case of any discrepancy between any deliverable and the Requirements Traceability Matrix (RTM), the controlling document shall be the RTM.

2.	In the case of any contradiction between deliverables, the contradiction shall be resolved at the sole discretion of DHSS.

NOTE: Deliverables will be reviewed by DHSS in a sequential manner.  A deliverable will not be accepted for review until the preceding deliverable has been approved. This provision does not prohibit the Contractor from working on multiple deliverables at the same time.

### Project Deliverables by Phase

Project deliverables are as follows. Milestones are indicated with the Mn designation.

|  | Project Deliverables & Milestones (M1-7) |
| --- | --- |
| Phase 1 - Planning | Deliverable: Baseline Project Plan |
|  | Deliverable: Document Templates |
|  | Deliverable: Requirements Management and Traceability Matrix (RTM) |
|  | Deliverable: Communications Plan |
|  | Deliverable: Data Migration Plan |
|  | Deliverable: Business Continuity Disaster Recovery (BCDR) Plan |
|  | Deliverable: CMS Certification Plan |
|  | Deliverable: Test Plan |
|  | Deliverable Training Plan |
|  | Deliverable: Implementation Plan |
|  | Approval of Phase 1 (M1) |
| Phase 2 - Design | Deliverable: Business Requirements Document (BRD) |
|  | Deliverable: Design Specifications Document (DSD) |
|  | Deliverable: Interface Specifications Document (ISD) |
|  | Deliverable: Requirements Traceability Matrix (RTM) |
|  | Approval of Phase 2 (M2) |
| Phase 3 - Development | Deliverable: Evidence of completion of Development/Configuration and Unit Testing cycles for modules/categories |
|  | Deliverable: Demonstrations of modules/categories |
|  | Deliverable: End to End Process Flows |
|  | Deliverable: Produce Requirements Traceability Matrix (RTM) |
|  | Deliverable: Implementation Plan |
|  | Approval of Phase 3 – Development (M3D) |
| Phase 4 - Test | Deliverable: Completed SIT |
|  | Deliverable: Completed Training Materials and Schedule |
|  | Deliverable: Completed UAT |
|  | Deliverable: CMS Operational Readiness Review (ORR) |
|  | Approval of Phase 4 – Test (M4T) |
| Phase 5 – Implementation | Deliverable: Performance and Quality Plan |
|  | Deliverable: Production System Acceptance |
|  | Deliverable: Produce Requirements Traceability Matrix (RTM) |
|  | Approval of Phase 5 (M5) |
| Phase 6 – Warranty Period | Deliverable: Conclusion of Warranty |
|  | Approval of Phase 6 (M6) |
| Phase 7 – CMS Certification | Deliverable: CMS Final Certification (CR) |
|  | Deliverable: Performance and Quality Plan |
|  | Approval of Phase 7 (M7) |

Except for the initial and final project phases above, Contractor may propose a different sequence of phases and deliverables. Schedule E1 of Exhibit E (Project Cost Forms) must reflect this different sequence.

### Phase 1

This phase is the kickoff of the project where the overall project planning, project management and schedule are agreed to and the ground rules and expectations are set.  In Phase 1, all deliverable documentation will be initially introduced in an “Outline and Sample Contents” template submitted by the Contractor. DHSS staff will approve each template. These templates may also be subject to federal review as well. Each deliverable will follow its respective approved template design.

The deliverables in this phase are:

#### Deliverable: Baseline Project Plan

This mandatory deliverable is the first update of the project plan submitted with the proposal of the selected Contractor. See Section 6.2.4 for a description of this deliverable.

The project plan is a living document and must be updated at the same interval as the status reports throughout the project to reflect actual project status and timelines.  DHSS must approve any change that results in the change of a milestone date.

#### Deliverable: Document Templates

This is a mandatory deliverable. Contractor must work with DHSS staff to design templates for each subsequent document deliverable including but not limited to requirement documents, detailed design documents, training plans, testing plans, status reports, issues tracking, executive meeting summaries and other project documents. These template designs are critical to ensuring that the deliverables and other project documents are in a format agreed to by all parties. Each template must be separately approved by DHSS. Each deliverable document will be submitted in the agreed upon template format.

A section of this document shall include the deliverable review process agreed to by DHSS and Contractor. This can be a restatement of Section 4.12.1 of this RFP or if the stated RFP process has been modified in any way, it must be documented in this deliverable.

With formal DHSS approval of all deliverables in this phase, the milestone payment (M1) minus 20% holdback may be invoiced.

Deliverable: CMS Certification Plan

The CMS Certification Plan must detail the objectives and strategy to support CMS Streamlined Modular Certification of the PASRR web-based system.  Both the Operational Readiness Review (ORR) and Final Certification (CR).  The Contractor’s CMS Certification Plan should include details of the planning, development and production phases required to meet DMMA’s certification objectives and CMS artifact and outcome measure requirements. See link below for details on this mandatory deliverable.

The CMS Certification will enable DMMA to align with the Medicaid IT Investment Lifecycle Engagement and Certification Process[1] as illustrated by CMS below. The Contractor’s CMS Certification Plan should include details of the planning, development and production phases required to meet DMMA’s certification objectives and CMS artifact and outcome measure requirements. See link below for details on this mandatory deliverable.

https://www.medicaid.gov/medicaid/data-systems/certification/streamlined-modular-certification/index.html

CMS’ Streamlined Modular Certification currently has the following certification elements:

- Conditions for Enhanced Funding for which states must ensure ongoing compliance.

- CMS-required outcomes, which are based on statutory or regulatory requirements to promote the efficient, economical, and effective administration of the state’s Medicaid program.

- State-specific outcomes that reflect the unique circumstances, characteristics, or program priorities which the state’s IT project will directly address.

- Metrics to provide evidence about whether the outcomes are achieved on an ongoing basis.

- Required Artifacts.

With CMS Certification both the ORR and CR achieved and formal DMMA approval of all deliverables in this phase, the milestone payments (M4 and M7) may be invoiced.

#### Deliverable: Communications Plan

This is a mandatory deliverable. This is a plan for effective and efficient communications across the project team. This includes stakeholders, business partners and the public if this is a public facing application.

#### Deliverable: Training Plan

This is a mandatory deliverable. This is a plan for training of staff involved in UAT plus training of staff for implementation. It will identify the type of training (I.e. train the trainer vs. train all and UAT training). It must include a Resource Allocation Matrix which is a schedule showing staff name, training type/class name, dates and times. It must also include a mechanism for surveying the effectiveness of the training.

The Contractor shall provide system training and maintain quality customer

service to DMMA throughout the Contract:

1. The Contractor will provide a Project Manager, subject matter experts,

and the appropriate number of technical support staff such that they are

available to talk directly with DMMA staff regarding any issues or

questions about the system during normal working hours, typically 8:00 AM –

4:30 PM EST Monday through Friday, excluding State Holidays.

2. The Contractor will provide initial system training to State staff and end

users.

3. The Contractor will provide ongoing training to State staff and end users

via a web-based training module located on the Vendor’s website/portal

so that non-state employees can access it.

4. The Contractor will provide ongoing training to State staff and end users

secondary to State authorized changes and upgrades to the system over

time.

5. The Contractor will provide system manuals and educational materials to

State staff and end users. These materials will be updated to reflect

PASRR program or web system changes immediately and training will be

provided to State staff and end users to ensure compliance.

6. The Contractor will provide updates to the software as needed to align

with any CMS regulatory changes. Training to State staff and end users

will be provided to ensure compliance.

7. Ability for State staff to access on demand Learning Management System

reports of Level I Screener training.

Phase 2 - Design

Deliverable: Requirements Traceability Matrix (RTM)

This is a mandatory deliverable. Tracing forward, it is a matrix tracing the business requirements through detailed design, test scripts for SIT and UAT and the verification scenarios used to prove out the functionality of the implemented system. Tracing backward, it can be used for issue analysis and defect tracing. This is a living document that is updated as then project proceeds through its different phases.

#### Deliverable: Business Requirements Document (BRD)

This is a mandatory deliverable. This document consolidates the business requirements agreed upon from a series of requirements gathering sessions hosted by the Contractor. These are English-language requirements that serve as the basis for the RTM and may include as-is, to-be and gap analysis as part of a business re-engineering task. This is an important consideration especially with a COTS or system transfer where the business process will be updated to reflect the process flows within the new system. Each requirement must be numbered for mapping in the RTM. This document will also include a logical data model and process flow diagrams. This document may also include high level screen designs.

#### Deliverable: Design Specifications Document (DSD)

This is a mandatory deliverable. This document is based on the approved FRD and specifies a detailed system design which may include screen designs, system flow diagrams, database design, physical data model, ERD (as applicable), code table values, database scripts, rules engine scripts (as applicable), coding design templates (as applicable), hardware and software specification lists including procurement and out-year costs, architecture diagram(s) and other system specifications as agreed upon.

With formal DHSS approval of all deliverables in this phase, the milestone payment (M2) minus 20% holdback may be invoiced.

### Phase 3 - Development

#### Deliverable: Test Plan

This is a mandatory deliverable. This is a plan for testing of developed code in each of the environments (Unit, SIT, UAT and Production). It must include a section on reporting system issues, analysis and identification of defect, assignment of severity level, defect remediation and regression testing. This must also identify the mechanism for tracking issues and defects over time. The Test Plan must describe the approval process for code promotion from SIT to UAT and from UAT to Production.

The Contractor is responsible for providing UAT test scripts along with each application module deliverable.

#### Deliverable: Implementation Plan

This is a mandatory deliverable. This is the plan for the events leading up to and including implementation. It must include a readiness checklist and a step-by step schedule and decision points for the actual process. This will include a go/no-go decision process and the responsible parties. This will also include the acceptance criteria for the formal DHSS approval of the implemented system.

With formal DHSS approval of all deliverables in this phase, the milestone payment (M3) minus 20% holdback may be invoiced.

### Phase 4

#### Deliverable: Completed SIT

This deliverable consists of formal DHSS approval of System Integration Testing as outlined in the Test Plan.

#### Deliverable: Completed Training Prior to Go Live

This deliverable consists of formal DHSS approval of Training prior to go-live as outlined in the Training Plan. This will include a training effectiveness survey conducted towards the conclusion of training that will make recommendations on post go-live training.

#### Deliverable: Completed UAT

This deliverable consists of formal DHSS approval of User Acceptance Testing as outlined in the Test Plan.

Deliverable: Completed CMS Operational Readiness Review (ORR)

This deliverable consists of formal CMS approval of our ORR.

With formal DHSS approval of all deliverables in this phase, the milestone payment (M4) minus 20% holdback may be invoiced.

### Phase 5

#### Deliverable: Production System Acceptance

This deliverable consists of formal DHSS approval of the implemented production system that functions according to the approved design. This coincides with the onset of the warranty timeframe.

Onsite warranty support is not required for hosted solutions.

The Contractor will supply one year of warranty support after formal DHSS approval of the implemented system.  The warranty timeframe provides for issue resolution, bug fixes and system functionality problems with the new system. This support is included in the firm fixed price. Ongoing support costs may start to accrue at the onset of the warranty timeframe.

All issues identified during the warranty timeframe will be documented and vetted to determine if they are project defects traceable to agreed-upon system functionality. The Contractor will resolve these project defects at no charge to DHSS. A prioritized list of warranty defects will be maintained until all are resolved. Unresolved defects may be removed from this list only by agreement by DHSS. Non-warranty defects or change requests outside of project scope will be maintained on a prioritized M&O change list. Any defects identified after the warranty timeframe will be maintained on the prioritized M&O change list.

### Phase 6 and Phase 7

#### Deliverable: Conclusion of Warranty

The Contractor will deliver an Implementation/Warranty Closeout Report two weeks prior to the conclusion of the warranty timeframe that discusses overall system health, user satisfaction, on-going issues and challenges and recommendations for future changes/enhancements.

With formal DHSS approval of all deliverables in this phase, the milestone payment (M6) may be invoiced. The total M6 payment is the sum total of the holdbacks from milestone payments M1 thru M7 See section 7.1 for details on project payments.

Deliverable: CMS Final Certification (CR)

Failure to receive Certification at the earliest certification schedule approved by CMS and DMMA retroactive to implementation will constitute failure to substantially perform and will result in the assessment of damages. The certification date, which is determined by CMS, is not appealable and cannot be challenged by the Contractor.

Penalty  Damages for failure to meet the standard will equal the difference between the 75% allowable Federal Financial Participation (FFP) for operations and the 50% FFP available to the State for operations without certification. The damages will be assessed for any period of time that the system cannot receive the enhanced FFP.

## Project Expectations

Contractor will be expected to address the following requirements in detail. Emphasis is on the limited availability of DHSS staff for this project and the expectation that the Contractor express in detail their understanding of their responsibilities in the areas of Customization/Development, Implementation, Warranty, Training, and Deliverables.

DHSS’ strong preference is for vendors to bid remotely hosted (off-prem) solutions; however, this is not a mandate. If proposing a DHSS hosted (on-prem) solution, vendor must provide justification as to why the State will consider this over the stated off-prem preference.

### Site Requirements

DHSS prefers the use of web browser-based applications and given the option between browser-based applications and other types of applications, will select the browser-based solution.

DHSS prefers to purchase third party hardware and software directly unless there is significant advantage to DHSS in having the hardware/software as Contractor deliverables. In either case, all software licenses must be in the name of DHSS and must provide for separate development, test and production environments.

### DHSS Hosted Solutions

Contractors will address the following only if all or parts of the application will be housed at the Biggs Data Center. This includes components installed on DHSS workstations or servers.

The application and database infrastructure and platforms must be located at the Biggs Data Center on the DHSS Herman Holloway Sr. Health & Social Services Campus in New Castle, Delaware.

The following separate, isolated regions – in addition to the production region – are required for ongoing maintenance and system enhancements.

At a minimum:

- Unit test/Sand box (developers only)

- Integration test (developers only)

- UAT – prod sized (users only)

Optional development environments:

- A development region for major system enhancement projects

- A development region for ongoing maintenance

- A testing region where business analysts can regression test major systems enhancements

- A training region

When a web-browser-based solution is not available, DHSS runs all "thick client" applications (sometimes referred to as "client/server applications") on the Citrix XenApp/Metaframe platform. Contractor proposing such applications must ensure full Citrix XenApp/Metaframe compatibility. DHSS has infrastructure in place to present Citrix based applications to internal network users and/or external users via the Internet.

Any remote access by Contractor will be accomplished through the use of SSL VPN.  If Contractor expects or requires remote access for proper implementation and/or support of their solution, the proposal must detail the exact nature of the remote access required and why it cannot be accomplished through other means. Contractor should note that under no circumstances is "remote control" of user desktops ever allowed and the State of Delaware firewall will block such access.  Remote access to DHSS servers can only be permitted if the server resides within a DHSS/DTI DMZ. SSL/VPN must be used.

If the Contractor will use any third-party products during the course of this project, such products must be approved in writing by DHSS prior to their use.  In order to receive such approval, the Contractor is required to submit a list of the products, the number of licenses that will be procured (if applicable), and a description of how the product will be used. The description must include whether the product is only required for customization/development or whether it would be required for ongoing support/maintenance. Each product must also have an outline as to its initial and ongoing costs (including, but not limited to, licensing, maintenance, support, run time licensing versus developer licensing, and so on). Approval of third-party products is ultimately at the discretion of DHSS. Note: Because of potential liability and support issues, open-source products may only be proposed for this project if they are fully supported and insured by the Contractor. If proposing open-source software, Contractor will also propose alternate fully supported software serving the same/similar function(s).

Any software purchased or developed for DHSS must be an appropriate fit into the DHSS IT Environment as described in the DHSS Information Technology Environment Standards. Contractor will describe how their proposal's components are consistent with the current environment.  Contractor may propose solutions that are not consistent with the current environment but, in that case, must include a detailed analysis of how their solution's requirements will be integrated into the existing DHSS IT Environment (including, but not limited to, purchases required, set up requirements and so on). DHSS wishes to leverage the existing infrastructure at the Biggs Data Center to the extent possible. Contractor will describe how their system will take advantage of the existing infrastructure. All proposals (and/or their attendant integration suggestions) will be evaluated for their fit into the current environment. Utilization of this infrastructure will be a factor in proposal evaluation.

In addition to the required environments listed above, additional staging areas may be proposed at the discretion of the Contractor.  Contractor will address how each of these environments will be set up and utilized. These environments will be maintained for the life of the system. Proposals must provide for adequate ongoing licenses to maintain each environment.

### Remotely-Hosted Solutions

For remotely-hosted solutions the following separate, isolated regions – in addition to the production region – are minimally required for ongoing maintenance and system enhancements:

- A development region for ongoing maintenance

- A prod-sized UAT region

- A training region

### Environment Responsibilities

Contractor will propose which party (DHSS or Contractor) will have responsibility for each of the following environments. For remotely hosted solutions, the Contractor will normally assume full responsibility for each environment. Responsibility for DHSS hosted solutions are usually shared but must be clearly documented in the contact. For DHSS hosted solutions that will be maintained by the Contractor, Contractor is expected to maintain all regions under the direction of IRM.

### Unit Testing

This is a developer-controlled region where developers directly test created or modified modules. Users will not have access to this environment.  It is considered dynamic and unstable. Backup and restoration is at the option of the Contractor. IRM should only be involved with this environment if it is locally hosted.

### System Integration Testing

This is a developer-controlled region where developers directly test functional areas of the application comprising one or modules. Developers will create test scripts.  Users will not have access to this environment. This environment should be backed up. If this environment is locally hosted, IRM should be consulted for large scale batch runs that could affect other systems. To the extent possible, the Contractor should run the UAT scenarios in the SIT region so that defects are remediated prior to migration to UAT. For locally hosted solutions, Contractor will be expected to configure a local SIT environment for testing prior to migration to UAT. Migration to UAT can only be scheduled after DHSS has formally approved SIT test results.

### User Acceptance Testing (UAT)

System users directly test functional areas of the application as a precursor to production migration. This region is maintained by the Contractor. Testing will be scripted. This environment must be backed up and be fully recoverable. The environment must be architected and sized as a production copy. Converted production data will be used to populate the database. If this environment is locally hosted, IRM may or may not be involved in its maintenance.

Each system module will undergo UAT by DHSS prior to production implementation. DHSS and Contractor are jointly responsible for developing UAT test scenarios. However, DHSS is not limited to these scenarios and will test all aspects of deliverables. The locations for UAT DHSS staff will be at DHSS’ discretion. Acceptance criteria for approval will be documented and based upon the RTM. Additional acceptance criteria beyond what is specified in the RTM may be specified by DHSS, documented and agreed to prior to the start of UAT. Contractor cannot be held responsible for criteria that is not properly documented. Upon formal DHSS approval of all UAT scenarios in a module, it may be scheduled for migration into the production environment. For a locally hosted UAT environment, IRM will be involved as necessary in these migrations.

As a necessary part of UAT, end to end regression testing will be conducted by DHSS. This testing must be completed, and the results approved by DHSS prior to production implementation.

As UAT is a responsibility of DHSS, Contractor is prohibited from participating in the UAT process except for readiness activities such as data refresh and running any batch jobs associated with the testing. Contractor will not be involved in the evaluation of the testing results or in the actual approval process.

### Production Implementation

Prior to implementation, the Contractor will produce an implementation plan document to be reviewed and approved by DHSS. This document will contain a schedule listing pre through post implementation tasks, start & end dates/times, and responsible parties. The plan must address backup and recovery strategies along with periodic checkpoints to hasten recovery and restarts if needed. The document will list all primary participants along with backups, their email addresses and at least two phone numbers for each. Escalation procedures must be addressed as well. Actual implementation may be scheduled following DHSS approval of this document.

### Legacy Data Conversion

Legacy data conversion is a requirement under this contract. The business will have to consider what legacy data is necessary for conversion and what legacy data can be archived. If data will be archived, a retrieval solution must be designed and implemented. Consideration must be given to ETL (Extraction, Transformation and Loading) processes for conversion. The Contractor will be required to provide a data model in Microsoft Visio format. Conversion controls, especially the monitoring and proof of initial conversion results, are very important to ensure that the transactional source data converted into the system is accurate prior to implementation. Initial and ongoing conversion controls and balancing procedures must be described.

The quality of the legacy data must be assessed. Assuming that data cleanup will be necessary, Contractor will indicate in this section what data cleanup processes they will be responsible for and what processes DHSS will be responsible for. Data cleanup must be completed prior to UAT and should be substantially complete as early as possible in SIT. This must be reflected in the baseline project plan.

### Training

Training will be outlined in a training plan deliverable discussing expectations and schedules. A training planning session must be held to review the training plan prior to the first actual training session. This will enable DHSS/DMMA and Contractor staff to better communicate during these sessions. Contractor will detail in their proposal a training plan outline and schedule for users of each component of the system. The Contractor shall provide system training and maintain quality customer service to DMMA throughout the Contract:

1. The Contractor will provide a Project Manager, subject matter experts, and the appropriate number of technical support staff such that they are available to talk directly with DMMA staff regarding any issues or questions about the system during normal working hours, typically 8AM –5PM EST Monday through Friday, excluding State Holidays.

2. The Contractor will provide initial system training to State staff and end

users.

3. The Contractor will provide ongoing training to State staff and end users

via a web-based training module located on the Vendor’s website/portal

so that non-state employees can access it.

4. The Contractor will provide ongoing training to State staff and end users

secondary to State authorized changes and upgrades to the system over

time.

5. The Contractor will provide system manuals and educational materials to State staff and end users. These materials will be updated to reflect

PASRR program or web system changes immediately and training will be

provided to State staff and end users to ensure compliance.

6. The Contractor will provide updates to the software as needed to align

with any CMS regulatory changes. Training to State staff and end users

will be provided to ensure compliance.

7. Provide the Ability for State staff to access on demand Learning Management System reports of Level I Screener training.

### System User

Contractor will be responsible for training users in all aspects of the new system.  As applicable, Contractor will also include organizational change management-specific instruction to include old vs. new ways of conducting business with the new system. Training will demonstrate business and system workflows. System policy compliance (including any recent policy changes) will be covered.  If the new system is a replacement for a legacy system, training will also cover legacy vs. new system workflows and screens.

### Technical

Contractor will be responsible for training DHSS technical staff on all technical aspects of system operations and support including any third-party products. A key component to technical training is knowledge transfer. In their response to this section, Contractor will include a detailed discussion of their approach to knowledge transfer for technical staff.

### Maintenance and Operations (M&O)

Contractor must include a description of the ongoing M&O support they are proposing. Support includes licenses, help desk support, bug fixes and scheduled releases. Costs for such services will need to be shown in the Business Proposal. Support cost inflation is discussed on the cost forms.

Contractor must guarantee that their proposed solution will comply with all mandatory requirements throughout the entire support phase.  Contractor will also specify expected deadline dates for completion of such modifications after the provision of detailed, written notice of impending changes from the Division.

Contractor must also address the following in their proposal:

- Identify the average of your response and resolution times.  Provide examples of current measurements and metrics.

- Describe your process for providing application fixes and enhancements.

- Identify your average turnaround time for fixes and enhancements.

- Confirm whether or not clients have the opportunity to provide input into the prioritization of new features and enhancements.

- Identify your anticipated schedule for new releases and updates from the current date thorough the next three years.

- Confirm whether you have User Conferences and/or Advisory Boards.

It is critical that the proposed solution include ongoing support services and assurance that all regulatory requirements will be met for the Division. Other details and specific requirements are included in various sections throughout this RFP.

If the product is a COTS customizable solution, Contractor will provide an estimate of the number of hours required to apply the DHSS customization features to new releases. This and the cost information will need to be provided in the Business Proposal.

Contractor must guarantee that their proposed solution will comply with all mandatory requirements throughout the entire support phase. Contractor will also specify expected deadline dates for completion of such modifications after the provision of detailed, written notice of impending changes from DHSS.

#### Contractor Maintained Applications Hosted at the Biggs Data Center

For Contractor maintained solutions hosted at the Biggs Data Center, the Contractor will be responsible for version releases in the SIT, UAT and Production environments at Biggs. Production releases for M&O will be coordinated with the IRM Base Technology group.

#### Separation of Duties

For new versions of the application, it is imperative that for Contractor-maintained solutions, even if hosted at the Biggs Data Center, that development staff with a direct interest in the modified modules, not be involved in the production implementation of these modules. Contractor will address their M&O implementation strategy in this section so that it satisfies this requirement.

### Documentation

The Contractor is responsible for providing documentation of the new system.  At a minimum, this includes user manuals and/or on-line help.  For non-COTS systems and for the customized components of COTS systems, the Contractor is also responsible for providing sufficient technical system documentation to permit DHSS to maintain the application.

### Software Escrow Agreement

For COTS & SaaS solutions (where the code will not become the property of DHSS), DHSS requires proof of a software escrow or similar agreement. Contractor will acknowledge in their proposal that they have or will have this agreement in force for the entire contract term for the proposed solution at the time of contract signature.

If the solution includes a third-party hosting Contractor providing Platform as a Service (PaaS), Contractor will describe their business continuity agreement with the third-party hosting Contractor.

### Copyrighted/Proprietary Software Inclusion

For solutions being developed with federal funds, there is a federal requirement that DHSS provide a complete copy of the end product(s) to other States upon request. If this includes any of the Contractor’s copyrighted/proprietary software, the license terms for this software must be disclosed as they would for any other third-party products necessary for development and operations. Contractor will describe any inclusion of their copyrighted/proprietary software into their proposed solution and will affirm in this section that their solution will comply with the federal transfer requirement with no restrictions. DHSS reserves the right to reject proposals with solutions that do not comply with the federal requirement.

### Miscellaneous Requirements

For public-facing web applications, there must be a Spanish language option at the logon screen for users to choose in order to display a Spanish language version of the application. Contractor will be responsible for any translation services necessary and must include an estimated cost for this in their proposal. Web applications must also demonstrate substantial W3C compliance for accessibility and standardization purposes. Finally, the application must demonstrate the capability to be read by screen reading software such as JAWS® or ZoomText®.

# Proposal Evaluation/Contractor Selection

## Process

DHSS will conduct a three-tiered review process for this project.  In the first tier, each Technical Proposal will be evaluated to determine if it meets the Mandatory Submission Requirements described in Exhibit F – Mandatory Submission Requirements Checklist.

Any proposal failing to meet those requirements is subject to immediate disqualification without further review.

All proposals meeting the mandatory submission requirements will be given to the DHSS Evaluation Team.

In the second tier, the Evaluation Team will perform Technical and Business Proposal Reviews.  The individual scores of each evaluator will be averaged to determine a final technical score and a final business score. Technical and Business scores will be summed to determine each Contractor’s final proposal score.

After the Evaluation Team completes its initial review and scoring, DTI may choose to review the top two (2) to five (5) scored proposals and provide comments and recommendations to the Evaluation Team which will be used in selecting the Contractors to demonstrate their proposed solution.

Contractor may be required to demonstrate their proposed solutions. The demonstrations will be used in the Evaluation Team’s final deliberations.

In the third tier, the Evaluation Team findings will be presented to an Executive Selection Committee. The Executive Selection Committee will review Evaluation Team findings.  A potential Contractor will be recommended to the Secretary, DHSS. Final selection is at the discretion of the Secretary or a designee.

## Proposal Evaluation and Scoring

The Technical and Business proposals of each Contractor will be evaluated and assigned points.  A maximum of 100 total points is possible.

### Mandatory Requirements

The Division Director or designee from the Office of the Secretary, Contracting and Procurement Unit will perform this portion of the evaluation.  Each proposal will be reviewed for responsiveness to the mandatory requirements set forth in the RFP.  This will be a yes/no evaluation and proposals that fail to satisfy all of the criteria of this category may not be considered further for the award of a Contract.  Specific criteria for this category are as follows: Contractor is required to address Section 4 “Contractor Responsibilities/Project Requirements” in detail by subsection and bullet.  Contractor is required to follow Section 6 “Contractor Instructions” explicitly and complete all required forms as instructed.

Failure to adequately meet any one (1) mandatory requirement may cause the entire proposal to be deemed non-responsive and be rejected from further consideration.  However, DHSS reserves the right to waive minor irregularities and minor instances of non-compliance.

### Technical Proposal Scoring

Only those Contractors submitting Technical Proposals which meet the Mandatory Submission Requirements provision will have their Technical Proposals scored.

### Business Proposal Consideration

The business proposal will be reviewed based on the costs submitted as part of the cost worksheet and on the documented stability and resources of the Contractor. Strong consideration will be given to how well the costs in the Project Cost Forms compare to the level of effort for this and other proposals along with the accuracy of the submitted figures. DHSS reserves the right to reject, as technically unqualified, proposals that are unrealistically low if, in the judgment of the evaluation team, a lack of sufficient budgeted resources would jeopardize project success.

### Contract Negotiation

Prior to contract signature, DHSS or the selected vendor may request to engage in a negotiations process to fine tune contract language to make it more suitable for the project. This process will be used to address the exceptions listed in Attachment 3 of   the RFP. Additional or modified contract language would go into a contract addendum document or would be edited into the original document as agreed upon by the parties.

DHSS reserves the right to develop performance standards and penalty provisions as part of this process.

# Contractor Instructions

## Submission Information

All proposals must be submitted via the DHSS e-Procurement portal at https://dhss.bonfirehub.com. Responses submitted by hard copy, mail, facsimile, or e-mail will not be accepted.

Confidential information

Any required confidential corporate financial/audit information or trade secrets may be included in a separate file entitled “Corporate Confidential Information”).

Each submission will contain the following files at a minimum:

- Submission Contents.doc (Microsoft Word 2000 or higher)

- RFP Technical Proposal.doc

- RFP Business Proposal.doc

- RFP Technical Proposal.pdf

- RFP Business Proposal.pdf

- Corporate Confidential Information (as applicable)

Each proposal file in PDF format must be a printable copy. Other files may be submitted separately. The Submission Contents.doc file will consist of a Word table listing each file submitted along with a short description of each.

It is the responsibility of the Contractor to ensure all submitted files are machine readable, virus free and are otherwise error-free. Submissions not in this condition may be cause for the Contractor to be disqualified from bidding.

### RFP and Final Contract

The contents of the RFP will be incorporated into the final contract and will become binding upon the successful Contractor.

### Proposal and Final Contract

The Contractor's proposal will be incorporated into the final contract and be considered binding upon the successful Contractor.

### Modifications to Proposals

Modifications to proposals will not be accepted after the submission deadline. At any time, DHSS reserves the right to request clarification and/or further technical information from any Contractor submitting a proposal.

### Alternative Solutions

The proposal must contain a single solution, including hardware and software. This is critical in ensuring project success and that project costs are expected, administered and contained. Contractors may propose alternative solutions but only as fully separate proposals that will be evaluated separately. Single proposals containing alternative/multiple solutions will be failed.

## Technical Proposal Contents

The Technical Proposal shall consist of and be labeled with the following sections:

##### Transmittal Letter

##### Required Forms

##### Executive Summary

##### Contract Management Plan

##### Contractor Responsibilities/Project Requirements

##### Staff Qualifications and Experience

##### Firm Past Performance and Qualifications

The format and contents for the material to be included under each of these headings is described below.  Each subsection within the Technical Proposal must include all items listed under a heading because evaluation of the proposals shall be done on a section-by-section or functional area basis.  No reference to, or inclusion of, cost information shall appear in the Technical Proposal or Transmittal Letter.

### Transmittal Letter (Section A)

The Transmittal Letter shall identify all materials and enclosures being forwarded collectively in response to this RFP. The Transmittal Letter must be signed by an individual authorized to commit the company to the scope of work proposed. It must include the following in the order given:

- An itemization of all materials and enclosures being forwarded in response to the RFP.

- A statement certifying that the proposal files have been scanned and are free from viruses and other malicious software.

- A reference to all RFP amendments received by the Contractor (by amendment issue date), to warrant that the Contractor is aware of all such amendments in the event that there are any; if none have been received by the Contractor, a statement to that effect must be included.

- A statement that price and cost data are not contained in any part of the bid other than in the Business Proposal

- A statement that certifies pricing was arrived at without any collusion or conflict of interest.

### Technical Proposal Required Forms (Section B)

Please include the following completed forms in this section. Additional required forms are discussed in sections 6.2.5, 6.2.6 and 6.2.7.

Certification Sheet and Statement of Compliance

Exhibit B: These are forms in which the Contractor must certify certain required compliance provisions.

Mandatory Submission Requirements Checklist

Exhibit F: This is the mandatory submission requirements checklist. Agreement to or acknowledgement of a requirement is shown by a Y (Yes) or N (No) next to the requirement and a signature at the bottom of the checklist. Failure to adequately meet any one (1) mandatory requirement may cause the entire proposal to be deemed non-responsive and be rejected from further consideration. However, DHSS reserves the right to waive minor irregularities and minor instances of non-compliance.

Contractor Contact Information

Exhibit J: This form must be completed and signed by prospective Contractors.

### Executive Summary (Section C)

Contractor shall present a high-level project description to give the evaluation team and others a broad understanding of the technical proposal and the Contractor’s approach to this project. This should summarize project purpose, key project tasks, a high-level timeline, key milestones, and qualifications of key personnel, along with subcontractor usage and their scope of work.  A summary of the Contractor's corporate resources, including previous relevant experience, staff, and financial stability must be included. The Executive Summary is limited to a maximum of ten (10) pages.

### Contract Management Plan (Section D)

Contractor shall describe the overall plan and required activities in order to implement the project within the budget and described schedule. This should include descriptions of management controls, processes and reporting requirements that will be put into place to ensure a smooth administration of this project.

#### High-Level Draft Baseline Project Plan (Section D.1)

As part of the proposal, Contractor must create a high-level draft baseline project plan with the following information:

Tasks, subtasks, dependencies, key dates including proposed dates for deliverable submission, DHSS deliverable approval, Federal deliverable approval (if required) and proposed payment milestones.

- Staffing structure, with a breakdown by activity, task and subtask within the entire project.

- A separate organization chart with staff names & functional titles.

Description at the subtask level including duration and required staff resources (Contractor vs. DHSS) and hours.

Resource staffing matrix by subtask, summarized by total hours by person, per month.

The high-level project plan must be created in Microsoft Project (mpp) format and converted to a pdf format for uploading into Bonfire. Contractor must also discuss procedures for project plan maintenance, status reporting, deliverable walkthroughs, subcontractor management, issue tracking and resolution, interfacing with DHSS staff and contract management.

See Project Plan Template in Information Technology Publications link in Exhibit C for a sample project plan in mpp format.

- This provides the general format that Contractor must follow when constructing the project plan. Project plan must reflect each deliverable and milestone in the specified format. Review periods as specified in the RFP must be built into the project schedule. As applicable, federal review timeframes must be included as project tasks. Serial deliverable review periods must be shown - the best way to do this is to link the "DHSS Review of Deliverable" task with the prior deliverable's review task.  The project plan is a critical deliverable and must reflect all dependencies, dates and review periods. If the plan has unresolved issues, DHSS will not approve the initial milestone payment.

A detailed, updated project plan will be created after contract signature and will serve as the initial deliverable and baseline project schedule. This is a critical milestone task, and all subsequent work will be dependent on the formal DHSS approval of the initial milestone. Until formal DHSS approval of this milestone, no other billable work on this project should take place. Unless otherwise extended by DHSS, a Baseline Project Plan must be submitted for DHSS approval within one month of the project start date. If there is no Baseline Project Plan submitted by this date, DHSS at its sole option may choose to take remedial action up to and including termination of the contract. Therefore, it is critical that this task be completed and approved as soon as possible. This project plan must include each phase of the project, clearly identifying the resources necessary to meet project goals. It will be the Contractor’s responsibility to provide complete and accurate backup documentation as required for all document deliverables. The project plan is a living document, and it must be updated and presented as part of the periodic status report to accurately reflect current project timelines and task progress. This is mandatory. The updated project plan must include the baseline start and end dates as columns alongside the current task start and end dates. If there are modifications to the project scope, there is a formal DHSS change request process for review and approval of these requests. Approved change requests must result in the addition of a re-baselined project plan as a project deliverable due within one month of signature of the contract amendment.

Status reports and project plans will be archived as part of the project artifacts in a central controlled Microsoft SharePoint environment.

- Contractor staff expertise in MS Project is critical for proper construction and maintenance of this plan.

- NOTE: All of the application deliverables are described at a module level.  The project plan must be detailed and include items such as:

- Project Kickoff Meeting

- Technical Briefing with IRM Staff

- Status meetings

- Functional Requirements JAD sessions

- Functional Requirements Deliverable (FRD) *

- Detailed System Design (DSD) JAD sessions

- DSD deliverable *

- User manual or on-line help *

- Systems documentation, as required *

- Training plan including test scripts *

- User Acceptance Testing *

- Operational Readiness Review (ORR) with CMS (pre-certification review)

- Production implementation *

- Final CMS Certification

- Conclusion of Warranty *

- For the items shown with an asterisk above, the plan needs to provide time for DHSS review and approval.

### Project Requirements (Section E)

Contractor must describe their understanding and approach to meet the expectations and mandatory requirements specified in Section 4. Address bulleted and titled requirement paragraphs within subsections as “Bullet n” and “Paragraph Title” respectively. Please address DHSS staffing considerations in subsections where staffing is mentioned. Please complete Crosswalk of RFP Section 4 form (Exhibit G) and include in this section.

### Staff Qualifications and Experience (Section F)

Contractor shall submit a staff skills matrix in their own format to summarize relevant experience of the proposed staff, including any subcontractor staff in the areas of:

- Technical project management

- Planning

- Requirements Analysis

- Project Management

- Certification Manager and staff

Additionally, Contractor shall provide a narrative description of experience each key staff member has in the areas relevant to this project. Contractor and subcontractor staff shall be separately identified. Contractor staff requirements will be addressed as outlined in subsection 4.1. Resumes will be formatted as outlined in Exhibit D and included in this section of the proposal. Contractor must also provide an organization chart of all proposed staff.

If subcontractors are being proposed, then include the name and address of each sub-Contractor entity along with an organization chart indicating staffing breakdown by job title and staff numbers on this project. This organization chart must show how the individual subcontractor entity will be managed by your firm as the primary Contractor.  Any sub or co-Contractor entity(s) proposed will need prior approval by DHSS before the contract is signed. If proposing no subcontractors, please state in this proposal section “No subcontractors are being proposed as part of this contract.” Please refer to RFP Exhibit A for subcontractor standards.

### Firm Past Performance and Qualifications (Section G)

Contractor shall describe their corporate experience within the last five (5) years directly related to the proposed contract.  Also include experience in:

- Other government projects of a similar scale.

- Validation of other CMS Certified projects.

Experience of proposed subcontractors shall be presented separately.

Provide a summary description of each of these projects including the contract cost and the scheduled and actual completion dates of each project. For each project, provide name, address and phone number for an administrative or managerial customer reference familiar with the Contractor’s performance. Please use the Contractor Project Experience form (Exhibit H) to provide this information in this section.

Provide an example of an actual client implementation plan, similar in magnitude to the PASRR, including staff, dates, milestones, deliverables, and resources.

### Policy Memorandum Number 70 (Section H)

Please review DHSS Policy Memorandum Number 70. The link to this document is in Exhibit C. If your firm has a written inclusion policy/plan, please acknowledge it in this section and include a link to this document if possible.

If your firm does not have an inclusion policy/plan, please respond to this section as follows, “Contractor does not have an inclusion policy/plan”.

The response to this section will have no impact on the scoring of your proposal.

### RFP Exhibits (Section I)

Please place the completed RFP Exhibits in this section of the proposal.

## Business Proposal Contents

The business proposal will contain all project costs along with evidence of the Contractor’s financial stability.

### Project Cost Information (Section J)

Contractor shall provide costs for the project as outlined in Exhibit E.

In completing the cost schedules, rounding should not be used.  A total must equal the sum of its details/subtotals; a subtotal must equal the sum of its details.

The Total Project Cost shown in Schedule E1 must include all costs that the selected Contractor will be paid by DHSS under this contract.

See the Deliverable Cost Schedule Template in Information Technology Publications link in Exhibit C for a sample file in xls format.

Cost information must only be included in the Business Proposal. No cost information should be listed in the Technical Proposal.

### Software and Hardware Information (Section K)

On a separate page of the Business Proposal entitled “Software Licensing Structure” list each module and each third-party software application listed in either Schedule E1 or Schedule E4.  Describe what required (or optional) functions from section 4 that the particular module or application includes. Discuss the licensing structure (per seat, concurrent user, site, etc.) for each.

On a separate page of the Business Proposal entitled “Hardware Description” list each hardware item listed in either Schedule E1 or Schedule E5.  Provide a description of its function and a detailed component list.

All licenses must be in the name of the State or DHSS and at a minimum must provide for separate development, test and production environments.

#### Procurement Instructions

Contractor will work with a State-approved hardware/software Contractor(s) to develop and verify the specifications for project hardware and software.  The State approved Contractor will send the Contractor a product specifications list, without cost information, for confirmation. The Contractor will submit the confirmed list to DHSS and DHSS will request a quote from the Contractor(s). The State-approved Contractor will develop the quote using these specifications and send this to DHSS. The Division will process the purchase (order) as normal, using project funds. This will ensure the products are in the State or DHSS’ name and are added to our current agreements.

### Contractor Stability and Resources (Section L)

Contractor shall describe its corporate stability and resources that will allow it to complete a project of this scale and meet all the requirements contained in this RFP.  The Contractor’s demonstration of its financial solvency and sufficiency of corporate resources is dependent upon whether the Contractor's organization is publicly held or not:

If the Contractor is a publicly-held corporation, enclose a copy of the corporation's most recent three years of audited financial reports and financial statements, a recent Dun and Bradstreet credit report, and the name, address, and telephone number of a responsible representative of the Contractor's principle financial or banking organization; include this information with copy of the Technical Proposal and reference the enclosure as the response to this subsection; or

If the Contractor is not a publicly-held corporation, the Contractor may either comply with the preceding paragraph or describe the bidding organization, including size, longevity, client base, areas of specialization and expertise, a recent Dun and Bradstreet credit report, and any other pertinent information in such a manner that the proposal evaluator may reasonably formulate a determination about the stability and financial strength of the bidding organization; also to be provided is a bank reference and a credit rating (with the name of the rating service); and

Disclosure of any and all judgments, pending or expected litigation, or other real or potential financial reversals, which might materially affect the viability or stability of the bidding organization; or warrant that no such condition is known to exist.

This level of detail must also be provided for any subcontractors(s) who are proposed to complete at least ten (10) percent of the proposed scope of work.

The requirements from RFP Section III.B General Evaluation Requirements must be addressed and consolidated into this section.

# Terms and Conditions

The following provisions constitute the terms and conditions of the contractual agreement between DHSS and the Contractor. This section contains terms and conditions specific to this RFP. The general terms and conditions are contained in Exhibit A.

## Payment for Services Rendered

Design, Development and Implementation (DDI) Services will be bound by a firm fixed price. The firm fixed price will be the Total DDI cost shown in Schedule E1 (Exhibit E).  Based upon the Contractor's satisfactory completion and formal DHSS approval of the identified scheduled payment milestones, the Contractor may invoice DHSS.

Contractors are to propose their operations compensation rates using Exhibit E3 of this RFP. Proposed compensation rates will be based on an estimated 12,000 Level I Screens per year. Estimated Clinical Reviews at 5,000 per year. Independent Evaluations for Level II are estimated at 1,200 per year. Specialized Services and Care Planning Monitoring is 180 reviews per year. The state prefers to be billed per item performed each month. However, to assess maximum possible contract cost the above maximum quantity estimates are used to identify the total proposed contract cost and to set the maximum value of purchase orders.

Support costs must be categorized separately in the invoice and allow the state to identify,  at minimum, the monthly cost for the following categories of services.

- Level 1 Screenings

- Level 1.5 Clinical Reviews

- Level 2 Independent Evaluations

- Specialized Services and Care Planning Monitoring

The state will require operational invoicing to broken out so that we can identify these categories because we receive different federal financial participation for level 2 reviews. Additionally,  from an accounting perspective, we need to assign the share of cost between DMMA, DSAMH, and DDDS based on types of activities performed.

If DHSS and Contractor agree to a project scope modification that involves a change (increase or decrease) to the firm fixed price, a contract amendment will be executed to account for the modification to the firm fixed cost along with any other changes required to the project artifacts.

## Contractor Personnel

At any time and at its sole discretion, DHSS shall have the right to require the Contractor to remove any individual (either Contractor or subcontractor) from his/her assignment to this contract if, in the opinion of DHSS, such employee is uncooperative, inept, incompetent or otherwise unacceptable. DHSS will notify the Contractor of this issue in writing and Contractor will immediately comply. DHSS shall not be invoiced for any further work by this individual after this notification. If the Contractor must make a staff substitution for whatever reason, a staff person with equivalent or better qualifications and experience will be proposed to DHSS as soon as possible. This proposed candidate will be subject to the same qualifying procedures as the original candidate. The DHSS Project Director and Project IRM Manager must approve this substitution before their term on the project begins. If a staff position becomes temporarily or permanently vacant for any reason, including the Contractor’s choice to reassign a staff member, DHSS may reduce payments to the Contractor in the amount equal to the vacated positions pay rate for the time period the position is vacant. DHSS may choose to waive its right to reduce payments if the proposed replacement staff member can be approved and can assume the vacated position immediately upon its vacancy.

## Funding

This contract is dependent upon the appropriation of the necessary funding.

DHSS reserves the right to reject or accept any bid or portion thereof, as may be necessary to meet its funding limitations and processing constraints.

## Confidentiality

The Contractor shall safeguard any client information and other confidential information that may be obtained during the course of the project and will not use the information for any purpose other than the Contract may require.

## Contract Transition

In the event DHSS awards the contract to another Contractor, through contract expiration or termination of this contract, the Contractor will develop a plan to facilitate a smooth transition of contracted functions either back to DHSS or to another Contractor designated by DHSS. This transition plan must be approved by DHSS.

## Professional Services Agreement (PSA) Template

This is the statewide template which is the basis for the contract with DHSS. The link to this document is in Exhibit C. Bidders are instructed to review this document. All provisions in this template are to be treated as mandatory. Any exceptions to the PSA must be listed (along with the RFP exceptions) in the RFP Exception Form (Attachment 3).

## Contract Amendments

If it will be necessary to amend the contract, the State will provide requirements to the Contractor and the Contractor will provide a proposal in response to those requirements. Contractor may be bound to rates detailed in a prior contract. Contractor will attach to their proposal a current copy of the Delaware business license along with signed copies (as applicable) of the DTI CSA and a signed copy of the State BAA.

# Exhibits

Exhibits referenced in this RFP are included in this section. The following are included for the Contractor’s use in submitting a proposal.

#### A. General Terms and Conditions

#### B. Certification Sheet and Statement of Compliance

#### C. Website Links

#### D. Key Position Resume

#### E. Project Cost Forms

#### F. Mandatory Submission Requirements Checklist

#### G. Crosswalk of RFP Section 4

#### H. Contractor Project Experience

#### I. Deliverable Acceptance Request (DAR)

#### J. Contractor Contact Information

#### K. Criminal Background Check Instructions

#### L. CMS Certification

#### M.2015 PASRR National Report

#### N. Delaware Medicaid State Plan

#### O. Review of State PASRR

#### P. State Nursing Facility Medical Necessity Requirements

#### Q. Performance and Quality Reporting

The following Exhibits must be completed by Contractor and provided as instructed below.

- Exhibits B, D, F, G, H - Include in the Technical Proposal.

- Exhibit J - Email to the following RFP Lead address on or before the date of the mandatory pre-bid meeting.

- Mary E. Marinari, Sr. Administrator, DMMA Information System Unit

- Mary.marinari@delaware.gov

- Exhibit E - Include in the Business Proposal.

Exhibit

- General Terms and Conditions

General Terms and Conditions

#### The following provisions are applicable to all DHSS RFPs.

Investigation of Contractor's Qualifications

The State of Delaware may make such investigation as it deems necessary to determine ability of potential Contractors to furnish required services, and Contractors shall furnish the State with data requested for this purpose. The State reserves the right to reject any offer if evidence submitted or investigation of such Contractor fails to satisfy the State that the Contractor is properly qualified to deliver services.

Certifications, Representations, Acknowledgments

Using Exhibit B, bidding Contractors must certify that:

They are a regular dealer in the services being procured.

They can fulfill all requirements specified for development with this RFP.

They have independently determined their prices.

They are accurately representing their type of business and affiliations.

They have acknowledged any contingency fees paid to obtain award of this contract.

They have included in their quotation all costs necessary for or incidental to their total performance under the contract.

They will secure a Delaware Business License.

They will secure the appropriate type and amounts of insurance coverage required by the State. Proof of such coverage will be a requirement of the contract.

Right to a Debriefing

To request a debriefing on Contractor selection, the Contractor must submit a letter requesting a debriefing to the Procurement Administrator, DHSS, within ten days of the announced selection. In the letter, the Contractor must specifically state the reason(s) for the debriefing. Debriefing requests must be based on pertinent issues relating to the selection process. Debriefing requests based on specifications in the RFP will not be accepted. All debriefing requests will be evaluated in accordance with these conditions. Debriefing requests that meet these conditions will be reviewed and respectively answered by the Procurement Administrator and/or Debriefing Committee.

Hiring Provision

Staff contracted to provide the services requested in this RFP are not precluded from seeking employment with the State of Delaware.  The Contractor firm selected as a result of this RFP shall not prohibit their employees or subcontractor staff from seeking employment with the State of Delaware.

Anti Kick-back

The selected Contractor will be expected to comply with other federal statutes including the Copeland "Anti-Kickback Act" (18 U.S.C.874), Section 306 of the Clean Air Act, Section 508 of the Clean Water Act, and the Debarment Act.

- Federal Provisions

Americans with Disabilities Act - This Act (28 CFR Part 35, Title II, Subtitle A) prohibits discrimination on the basis of disability in all services, programs, and activities provided to the public and State and local governments, except public transportation services.

Royalty-Free Rights to Use Software or Documentation Developed - The federal government reserves a royalty-free, non-exclusive, and irrevocable license to reproduce, publish, or otherwise use, and to authorize others to use, for federal government purposes, the copyright in any work developed under a grant, sub-grant, or contract under a grant or sub-grant or any rights of copyright to which a Contractor purchases ownership.

Drug-Free Workplace Statement - The Federal government implemented the Drug Free Workplace Act of 1988 in an attempt to address the problems of drug abuse on the job. It is a fact that employees who use drugs have less productivity, a lower quality of work, and a higher absenteeism, and are more likely to misappropriate funds or services. From this perspective, the drug abuser may endanger other employees, the public at large, or themselves. Damage to property, whether owned by this entity or not, could result from drug abuse on the job. All these actions might undermine public confidence in the services this entity provides. Therefore, in order to remain a responsible source for government contracts, the following guidelines have been adopted:

a. The unlawful manufacture, distribution, dispensation, possession or use of a controlled substance is prohibited in the workplace.

b. Violators may be terminated or requested to seek counseling from an approved rehabilitation service.

c. Employees must notify their employer of any conviction of a criminal drug statue no later than five days after such conviction.

d. Contractors of federal agencies are required to certify that they will provide drug-free workplaces for their employees.

Transactions subject to the suspension/debarment rules (covered transactions) include grants, subgrants, cooperative agreements, and prime contracts under such awards. Subcontracts are not included. Also, the dollar threshold for covered procurement contracts is $25,000. Contracts for Federally required audit services are covered regardless of dollar amount.

- DHSS Policy Memorandum # 70

Please refer to Exhibit C for the link to this document.

The Contractor agrees to adhere to the requirements of DHSS Policy Memorandum # 70, (effective 7/18/2015), and Divisional procedures regarding the concept of an inclusive workplace which is accepting of diverse populations in our workforce and actively practices acceptance of diverse populations within our community, through our programs and services we provide to our clients. It is understood that adherence to this policy includes the development of appropriate procedures to implement the policy and ensuring staff receive appropriate training on the policy requirements. The Contractor’s procedures must include the position(s) responsible for the PM70 process in the Contractor’s organization. Documentation of staff training on PM70 must be maintained by the Contractor.

Exhibit

- Certification Sheet and Statement of Compliance

DELAWARE HEALTH AND SOCIAL SERVICES

REQUEST FOR PROPOSAL

CERTIFICATION SHEET

As the official representative for the bidder, I certify on behalf of the agency that:

a.  They are a regular dealer in the services being procured.

b.  They have the ability to fulfill all requirements specified for development within this RFP.

c.  They have independently determined their prices.

d.  They are accurately representing their type of business and affiliations.

e.  They will secure a Delaware Business License.

- They have acknowledged that no contingency fees have been paid to obtain award of this contract.

- The Prices in this offer have been arrived at independently, without consultation, communication, or agreement, for the purpose of restricting competition, as to any matter relating to such prices with any other Contractor or with any competitor.

- Unless otherwise required by Law, the prices which have been quoted in this offer have not been knowingly disclosed by the Contractor and prior to the award in the case of a negotiated procurement, directly or indirectly to any other Contractor or to any competitor; and

- No attempt has been made or will be made by the Contractor in part to other persons or firm to submit or not to submit an offer for the purpose of restricting competition.

- They have not employed or retained any company or person (other than a full-time bona fide employee working solely for the Contractor) to solicit or secure this contract, and they have not paid or agreed to pay any company or person (other than a full-time bona fide employee working solely for the Contractor) any fee, commission percentage or brokerage fee contingent upon or resulting from the award of this contract.

- They (check one) operate ___an individual; _____a Partnership ____a non-profit (501 C-3) organization; _____a not-for-profit organization; or _____for Profit Corporation, incorporated under the laws of the State of____________.

- The referenced bidder has neither directly or indirectly entered into any agreement, participated in any collusion or otherwise taken any action in restraint of free competitive bidding in connection with this bid submitted this date to Delaware Health and Social Services.

- The referenced bidder agrees that the signed delivery of this bid represents the bidder’s acceptance of the terms and conditions of this invitation to bid including all specifications and special provisions.

n.	They (check one): _______are or _____are not owned or controlled by a parent company.  If owned or controlled by a parent company, enter name and address of parent company:

__________________________________________

__________________________________________

__________________________________________

__________________________________________

Violations and Penalties:

Each contract entered into by an agency for professional services shall contain a prohibition against contingency fees as follows:

- The firm offering professional services swears that it has not employed or retained any company or person working primarily for the firm offering professional services, to solicit or secure this agreement by improperly influencing the agency or any of its employees in the professional service procurement process.

- The firm offering the professional services has not paid or agreed to pay any person, company, corporation, individual or firm other than a bona fide employee working primarily for the firm offering professional services, any fee, commission, percentage, gift, or any other consideration contingent upon or resulting from the award or making of this agreement; and

- For the violation of this provision, the agency shall have the right to terminate the agreement without liability and at its discretion, to deduct from the contract price, or otherwise recover the full amount of such fee, commission, percentage, gift or consideration.

The following conditions are understood and agreed to:

a.  No charges, other than those specified in the cost proposal, are to be levied upon the State as a result of a contract.

b.  The State will have exclusive ownership of all products of this contract unless mutually agreed to in writing at the time a binding contract is executed.

Date				 Signature & Title of Official Representative

Type Name of Official Representative

PROCUREMENT

STATEMENT OF COMPLIANCE

As the official representative for the Contractor, I

Certify that on behalf of the agency that _________________________

(Company name) will comply with all Federal and State of Delaware laws, rules, and regulations, pertaining to equal employment opportunity and affirmative action laws.  In addition, compliance will be assured in regard to Federal and State of Delaware laws and Regulations relating to confidentiality and individual and family privacy in the collection and reporting of data.

Authorized Signature:_____________________________________________

Title:____________________________________________________________

Date:______________________________________________________________

Exhibit

- Website Links (in alphabetical order)

- Business Associate Agreement (BAA)

http://dhss.delaware.gov/dhss/dms/cmp/files/hipaabp.pdf

- CMS Streamlined Modular Certification

https://www.medicaid.gov/medicaid/data-systems/certification/streamlined-modular-certification/index.html

- Critical Security Controls

https://www.cisecurity.org/controls/

- DHSS Information Technology Environment Standards

http://www.dhss.delaware.gov/dhss/dms/irm/files/dhss_it_environment.pdf

- DMMA Fair Hearing Decisions

DMMA Fair Hearing Decisions - Delaware Health and Social Services - State of Delaware

- DMMA Medical Assistance Services: Medicaid

DMMA Medical Assistance Services: Medicaid - Delaware Health and Social Services - State of Delaware

- Enterprise Standards and Policies

http://dti.delaware.gov/information/standards-policies.shtml

- Information Technology Publications

http://www.dhss.delaware.gov/dhss/DMS/itpubs.html

See section entitled “Supportive Documentation for Bidding on Proposals”

- Offshore IT Staffing Policy

OffshoreITStaffingPolicy (delaware.gov)

- Policy Memorandum 70 on Inclusion

http://dhss.delaware.gov/dhss/admin/files/PM_70.pdf

- Professional Services Agreement

httpsubcontract://mymarketplace.delaware.gov/documents/professional-services-agreement.docx?ver=0213

- Terms and Conditions Governing Cloud Services and Data Usage Agreement

https://webfiles.dti.delaware.gov/pdfs/pp/Terms and Conditions Governing Cloud Services and Data Usage Agreement.pdf

Exhibit

- Key Position Resume

Key Position Resume

Name:					Proposed Project Position:

Number of years’ experience in the proposed position:

Number of years’ experience in this field of work:

Detail Training/Education

(Repeat the format below for as many degrees/certificates as are relevant to this proposal. Dates between training/education may overlap.)

Degree/Certificate				Dates of Training/Education

Detail Experience

(Repeat the format below for as many jobs/projects as are relevant to this proposal.  Dates between jobs/projects may overlap.)

Job/Project:						Position:

From Date:						To Date:

Description of the tasks this person performed in this job/project.  Detail any state or government planning projects and specify the role of the person on each project.

Exhibit

- Project Cost Forms

E1. Project Costs by Deliverables & Milestones

Deliverable & Milestone Cost Schedule

| Phase | Project Deliverables & Milestones | Deliverable Cost | Phase Cost | 20% Holdback | Contractor Invoice Amount | Projected Approval Date |
| --- | --- | --- | --- | --- | --- | --- |
| 1 Planning | Deliverable: Baseline Project Plan | C2 |  |  |  |  |
|  | Deliverable: Document Templates | C3 |  |  |  |  |
|  | Deliverable: Requirements Management and Traceability Matrix (RTM) | C4 |  |  |  |  |
|  | Deliverable: Communications Plan | C5 |  |  |  |  |
|  | Deliverable: Data Migration Plan | C6 |  |  |  |  |
|  | Deliverable: Business Continuity Disaster Recovery (BCDR) Plan | C7 |  |  |  |  |
|  | Deliverable: CMS Certification Plan | C8 |  |  |  |  |
|  | Deliverable: Test Plan | C9 |  |  |  |  |
|  | Deliverable: Training Plan | C10 |  |  |  |  |
|  | Deliverable: Implementation Plan | C11 |  |  |  |  |
|  | DHSS Approval of Phase 1 (M1 = 5% of Total DDI Cost) |  | SUM(C2:C11) | D12*0.2 | D12-E12 | M1 Date |
| 2 Design | Deliverable: Business Requirements Document (BRD | C13 |  |  |  |  |
|  | Deliverable: Design Specifications Document (DSD) | C14 |  |  |  |  |
|  | Deliverable: Interface Specifications Document (ISD) | C15 |  |  |  |  |
|  | Deliverable: Requirements Traceability Matrix (RTM) | C16 |  |  |  |  |
|  | DHSS Approval of Phase 2 (M2 = 10% of Total DDI Cost) |  | SUM(C13:C16) | D17*0.2 | D17-E17 | M2 Date |
| 3 Development | Deliverable: Evidence of completion of Development/Configuration and Unit Testing cycles for modules/categories | C18 |  |  |  |  |
|  | Deliverable: Demonstration of modules/categories | C19 |  |  |  |  |
|  | Deliverable: End to End Process Flows | C20 |  |  |  |  |
|  | Deliverable: Produce Requirements Traceability Matrix (RTM) | C21 |  |  |  |  |
|  | Deliverable: Implementation Plan | C22 |  |  |  |  |
|  | DHSS Approval of Phase 3 (M3 = 10% of Total DDI Cost) |  | SUM(C18:C22) | D23*0.2 | D23-E23 | M3 Date |
| 4 Test | Deliverable: Completed SIT | C24 |  |  |  |  |
|  | Deliverable: Completed Training Materials and Schedule | C25 |  |  |  |  |
|  | Deliverable: Completed UAT | C26 |  |  |  |  |
|  | Deliverable: CMS Operational Readiness Reviews (ORR) | C27 |  |  |  |  |
|  | DHSS Approval of Phase 4 (M4 = 10% of Total DDI Cost) |  | SUM(C24:C27) | D28*0.2 | D28-E28 | M4 Date |
| 5 Implementation | Deliverable: Performance and Quality Plan | C29 |  |  |  |  |
|  | Deliverable: Production System Acceptance | C30 |  |  |  |  |
|  | Deliverable: Produce Requirements Traceability Matrix (RTM) | C31 |  |  |  |  |
|  | DHSS Approval of Phase 5 (M5 = 30% of Total DDI Cost) |  | SUM(C29:C31) | D32*0.2 | D32-E32 | M5 Date |
| 6 Warranty Period | Deliverable: Conclusion of Warranty | N/A |  |  |  |  |
|  | DHSS Approval of Phase 6 (M6 = 20% of Total DDI Cost) |  | N/A | N/A | SUM(E12:E32) | M6 Date |
| 7 CMS Certification | Deliverable: CMS Final Certification (CR) C35 |  |  |  |  |  |
|  | Deliverable: Performance and Quality Plan C36 |  |  |  |  |  |
|  | DHSS Approval of Phase 7 (M7 = 15% of Total DDI Cost) |  | SUM(C35:C36) | D37*0.2 | D37-E37 | M7 Date |
| Total DDI Cost |  | SUM(C2:C37) |  |  |  |  |
| Total Ongoing Support Costs For Base Contract Term (From Cost Schedule E3) |  | $ |  |  |  |  |
| Total Project Cost |  | SUM(C37:C39) |  |  |  |  |

Please fill out each of the costs and dates specified above. Computed costs will be in the manner specified. Milestone costs are a specified percentage of the Total DDI cost. Deliverable costs must total to the milestone cost. If DHSS decides to eliminate one or more deliverables from this project, the firm fixed price of the contract would be adjusted by subtracting the cost of the deliverable(s) to be eliminated. Reduction in the scope of an individual deliverable could result in a cost reduction as well. Deliverables that are roughly equal in scope can be swapped in/out in the design phase and maintain the firm fixed price of the contract.

The Total Project Cost shown in Schedule E1 must include all costs that the Contractor will be paid by DHSS under this contract.  The Total Project Cost figure constitutes the firm fixed price of the contract.

Deliverables and milestones in the project cost schedule above will be identified in the Baseline Project Plan deliverable along with the projected date of DHSS approval.

Contractor must complete the Projected Date column for each milestone and the dates must correspond to the dates provided in the high-level project plan.

Holdbacks are mandatory for every milestone with the exception of the final phase milestone. Holdbacks cannot be modified except by contractual agreement.

Milestone Cost Breakdown

- Mn = Total Cost for Phase n deliverables – 20% holdback

- M6 = Sum of M1 – M6 holdbacks

Costs for each task/deliverable listed must be specified along with the total cost of all tasks/deliverables in each specified phase.  Please check all figures for accuracy.

DDI costs will be invoiced only through identified milestones upon formal approval by the Division and IRM. DDI invoicing by any other manner is prohibited except by prior written consent of DHSS. As applicable, approved change orders shall be bundled into a single deliverable that will be added to the Phase 5 milestone in Schedule E1. The milestone cost, milestone holdback and invoice amount would be adjusted accordingly. This milestone would be invoiced via the prescribed process.

Software will be acquired by DHSS in the State’s or DHSS’ name. Estimated total costs are only to be included in Schedule E4.

Hardware will be acquired by DHSS in the State’s or DHSS name. Estimated total costs are only to be included in Schedule E5.

E2. Schedule of Rates for Project Staff

Contractor is to list the fully loaded hourly rate for each person bid.  These rates will be binding and will be used to estimate costs in the event of a change in project scope.  A fully loaded hourly rate is an hourly rate that encompasses all costs to the Contractor for providing additional services to DHSS as necessitated by for additional tasks not covered under the scope of this contract.  Costs included in this rate would be salary, overhead, lodging, travel, supplies, incidentals, etc. This rate would be used to apply against the hours estimated for each additional task proposed such that Task Hours * Rate = Task Cost.

| Job Title | Name | Fully Loaded Hourly Rate |
| --- | --- | --- |

E3.	Ongoing Support Cost Schedule

The Contractor will detail in this section what their responsibilities will be for ongoing support.

Total costs are to be capped at a 3% inflation rate per year. Cost for Years 1 - 5 will be included in the firm fixed price of the signed base contract. DMMA may choose to amend the contract for one (1) optional extension for a period of three (3) years, and then another one (1) optional extension for a period of two (2) years of support at its sole discretion. The cost for operations for the full 10-year term of the contract must be identified in this section.

Ongoing support costs are to be listed in the following schedule. Support costs must be categorized separately (i.e., Hosting, Tier 2 Support, Maintenance (up to n hours), etc.) and, at minimum, contain separate cost categories for the following:

- Level 1 Screenings

- Level 1.5 Clinical Reviews

- Level 2 Independent Evaluations

- Specialized Services and Care Planning Monitoring

The contractor can choose to add additional cost categories.

The state will require operational invoicing to broken out into these cost categories because we receive different federal financial participation for level 2 reviews. Additionally,  from an accounting perspective, we need to assign the share of cost between DMMA, DSAMH, and DDDS based on types of activities performed.

Note: Year 1 begins on the start date of the contract. Operations and maintenance begin the month after formal DMMA approval of the implemented production system that functions according to the approved design. The start of the warranty period will coincide with the start of operations and maintenance. The State expects DDI to fill most of year 1. Therefore, based on the contractors proposed work plan, there may not be a full year of operational cost in year 1.

Cost schedules have been provided to summarize the total maximum annual cost. Subtotals are requested for years 1 - 5, years 6 – 8, years 9 -10, and the maximum contract (years 1 – 10).

Ongoing Support Costs

| Cost Category | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 |
| --- | --- | --- | --- | --- | --- |
| Level 1 screenings (up to 12,000 per year) |  |  |  |  |  |
| Level 1.5 clinical review (up to 3,600 per year) |  |  |  |  |  |
| Level 2 onsite evaluations (up to 1,200 per year) |  |  |  |  |  |
| Cost Category n |  |  |  |  |  |
| Total |  |  |  |  |  |

Total Ongoing Support Costs For Base Contract Term (Years 1 - 5):

$ ___________

| Cost Category | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- |
| Level 1 screenings (up to 12,000 per year) |  |  |  |
| Level 1.5 clinical review (up to 3,600 per year) |  |  |  |
| Level 2 onsite evaluations (up to 1,200 per year) |  |  |  |
| Cost Category n |  |  |  |
| Total |  |  |  |

Total Ongoing Support Costs For Optional Extension Contract Term (Years 6 - 8):

$ ___________

| Cost Category | Year 9 | Year 10 |
| --- | --- | --- |
| Level 1 screenings (up to 12,000 per year) |  |  |
| Level 1.5 clinical review (up to 3,600 per year) |  |  |
| Level 2 onsite evaluations (up to 1,200 per year) |  |  |
| Cost Category n |  |  |
| Total |  |  |

Total Ongoing Support Costs For Optional Extension Contract Term (Years 9 - 10):

$ ___________

Total Maximum Support Cost for the Contract (Year 1 – 10):   _________________

Additional costs

Estimate of the number of hours required to apply the DHSS customization features to new releases: ____________.

Include a single fully loaded hourly rate which will apply to future customization beyond what is within the scope of this contract:

$ ___________

E4.	DHSS Purchased Third Party Software Schedule

Please list all third-party software products required for DDI through M&O. These licenses are for DHSS staff and users only. Contractor licenses are not to be included in this list. DHSS is not responsible for purchasing Contractor developer licenses. DHSS will purchase all software licenses on this list. Only new software or additional licenses for existing software being proposed for this project will be listed here. If the proposed software solution comprises multiple separately costed modules, please list them separately here. DHSS will purchase the software licenses from a third party, not the Contractor. The software listed here will be evaluated by DHSS technical staff for compliance with State standards.

| Software Description/Name | Version Number | # of Licenses | Required After Go-Live? (Y/N) |
| --- | --- | --- | --- |

Total Estimated DHSS Purchased Third Party Software Cost $ __________________

The above total estimated cost is a ballpark estimate only. The Contractor will not be held responsible for this figure. DHSS understands that with licensing costs can vary depending on GSA pricing, licensing structure and individual purchasing agreements.  This cost figure will be used as part of estimating the total project budget when justifying project costs for the State Office of Management and federal funding partners (as applicable). This cost is not to be included in Schedule E1.

E5. DHSS Purchased Hardware Schedule

This is a hardware summary schedule with a total estimated cost. Only new hardware or upgrades to existing hardware being proposed for this project should be listed here. This list of hardware will be evaluated by DHSS technical staff for compliance with DHSS standards. DHSS will purchase the hardware from a third party, not the Contractor.

| Hardware Description/Name | Quantity |
| --- | --- |

Total Estimated DHSS Purchased Hardware Cost $  __________________

The above total estimated cost is a ballpark estimate only. The Contractor will not be held responsible for this figure. DHSS understands that hardware costs can vary. This cost figure will be used as part of estimating the total project budget when justifying project costs for OMB and federal funding partners (as applicable). This cost is not to be included in Schedule E1.

Note: If no additional DHSS purchased hardware is necessary for the proposed solution, please put “N/A” in the first cell in this table.

Exhibit

- Mandatory Submission Requirements Checklist

Mandatory Submission Requirements Checklist

| Mandatory Submission Requirement | RFP Section | Compliance Y or N |
| --- | --- | --- |
| The bid is submitted as separate Technical and Business proposal files | Appendix B.6.1 |  |
| The proposal contains a single solution in terms of this project | Appendix B.6.1.4 |  |
| Contractor/Proposed Subcontractor has appropriate project experience | Appendix B.6.2.7 |  |
| Transmittal Letter signed by an authorized representative | Appendix B.6.2.1 |  |
| Proposal submission files have been scanned and are free from viruses and other malicious software. | Appendix B.6.2.1 |  |
| Contractor Agrees to Comply with the provisions specified in the General Terms and Conditions | Appendix B.Exhibit A |  |
| Completed Project Cost Forms | Appendix B.Exhibit E |  |
| Total project cost does not exceed cost cap | Appendix B.Exhibit E |  |
| Firm fixed price contract proposed | Appendix B.7.1 |  |
| Proposal includes required resumes | Appendix B.6.2.6 & Appendix B.Exhibit D |  |
| Technical proposal is submitted with a completed, duly signed and dated copy of the Mandatory Submission Requirements Checklist | Appendix B.6.2.2 & Appendix B.Exhibit F |  |
| Completed Crosswalk of RFP Section 4 | Appendix B.6.2.5 & Appendix B.Exhibit G |  |
| Completed Contractor Project Experience Form | Appendix B.Exhibit H |  |
| Completed Contractor Contact Information Form | Appendix B.Exhibit J |  |
| Compliance with HIPAA Regulations & Standards | Appendix B.4.3 |  |
| DHSS-Specific Security Requirements | Appendix B.4.4.5 |  |
| The Project Plan, Templates, BRD, DSD, Acceptance in Prod & Conclusion of Warranty are listed as project deliverables | Appendix B.4.11 |  |
| ACA Safe Harbor Additional Fee and basis have been specified in Exhibit E2. Please include the fees in this section. | Appendix B.Exhibit E2 |  |
| Include this mandatory requirement as applicable Contractor confirms that PII and/or ePHI is either encrypted at rest OR that they intend to purchase Cyber Liability Insurance. | Appendix B.4.4.5 |  |
| Include this mandatory requirement as applicable Contractor acknowledges that they have reviewed the CSA and DUA documents | Appendix B.Exhibit C. Terms and Conditions Governing Cloud Services and Data Usage Agreement |  |
| The Contractor has a Supplier Diversity plan currently in place. If applicable, please upload in Bonfire as requested. Note: The response to this statement, while mandatory, will have no effect on the evaluation of the Contractor proposal. | Appendix B.Exhibit F |  |
| The Contractor has diverse sub-Contractors as outlined in Attachment 8 Tier II Sub-Contractors. If applicable, please upload in Bonfire as requested. Note: The response to this statement, while mandatory, will have no effect on the evaluation of the Contractor proposal. | Appendix B.Exhibit F |  |
| Does the Contractor have a written inclusion policy/plan currently in place? If “Yes”, it is required that a clearly identifiable copy of the inclusion policy/plan be attached to your proposal as instructed in RFP Section 6.2.8. If applicable, please upload in Bonfire as requested Note: The response to this statement, while mandatory, will have no effect on the evaluation of the Contractor proposal. | Appendix B.6.2.8 |  |

| _________________________________________ Signature of Authorized Representative |  |
| --- | --- |
| _________________________________________ Title / Company | _______________ Date |

Exhibit

- Crosswalk of RFP Section 4

Crosswalk of RFP Section 4

| RFP Section | Proposal Section Number | Proposal Page Number |
| --- | --- | --- |
| 4 Contractor Responsibilities/Project Requirements |  |  |
| 4.1 Staffing |  |  |
| 4.2 Project Management |  |  |
| 4.3 Requirement To Comply With HIPAA Regulations and Standards |  |  |
| 4.4 Requirement to Comply with State Policies and Standards |  |  |
| 4.5 Reporting |  |  |
| 4.6 Performance |  |  |
| 4.7 Degree of Customization |  |  |
| 4.8 Backup and Recovery |  |  |
| 4.9 Disaster Recovery |  |  |
| 4.10 Specific Project Tasks |  |  |
| 4.11 Deliverables |  |  |
| 4.12 Project Expectations |  |  |

This crosswalk links the numbered RFP sections to the sections and page numbers of the Contractor’s proposal. Contractor must complete this crosswalk completely for each numbered section in Section 4.

Exhibit

- Contractor Project Experience

Contractor Project Experience

| Client |  |
| --- | --- |
| Contact Name |  |
| Telephone No. |  |
| Location Street Address/City State/ZIP |  |
| Location City/State |  |
| Type of Facility |  |
| Comparable Project Experience |  |
| Current Status (WIP/Complete) |  |
| Original Budget |  |
| Completed Budget |  |
| Original Schedule |  |
| Completed Schedule |  |
| Comments: |  |
| Use one page per client. All clients will be used as references and all projects must be completed or work in progress. For projects in progress, state the estimated final budget and schedule dates based on current status. The Contact must be an administrative or managerial customer reference familiar with the Contractor’s performance. |  |

Exhibit

- Deliverable Acceptance Request (DAR)

|  |  | Deliverable Acceptance Request (DAR) |
| --- | --- | --- |

| Division Name: |  |
| --- | --- |
| Project Name: |  |
| Project Phase: |  |
| Project Manager: |  |
| Contractor: |  |
| Contractor Project Manager: |  |

| Deliverable Name: |  |
| --- | --- |
| Delivery Date: |  |
| Expected Date of Response: |  |
| Actual hours worked and Cost incurred: |  |

Narrative of findings:

| Division Program Name: | Signature: | Date: |
| --- | --- | --- |
| Div. IT Liaison Name: | Signature: | Date: |
| IRM Name: | Signature: | Date: |

Exhibit

- Contractor Contact Information

Delaware Health and Social Services

Request for Proposal

Contractor Contact Information

The following information must be filled out and brought to the mandatory pre-bid meeting. If no pre-bid meeting is being held, please submit this according to the instructions in Section 8.

Multiple contacts may be specified.

Contractor Contact(s)

| Contact Name |  |
| --- | --- |
| Email Address |  |

Authorized Contractor Representative

| Printed Name |  |
| --- | --- |
| Signature |  |
| Phone Number |  |
| Email Address |  |

Exhibit

- Criminal Background Check Instructions

Criminal Background Check (CBC)

Contractor staff are required to request their own criminal history. For privacy reasons, the SBI and FBI will not mail the results to anyone except the requestor, so the results must be delivered to the DHSS Security Manager at the Biggs Data Center in a sealed envelope. Costs will be borne by the Contractor.

Please click here for instructions on Obtaining a Certified Delaware Criminal History.

Once the fingerprints are taken, the SBI office will provide fingerprint cards to you to mail to the FBI after they take the prints. It is your responsibility to mail the cards.

When you receive your SBI and FBI reports at your home address, DO NOT OPEN THE ENVELOPES. If you break the seal on the envelopes, you will be responsible to go through the process again at your own expense.

Mark envelopes as CONFIDENTIAL.

Either hand-deliver or mail the SEALED FBI and SBI envelopes to:

DHSS Security Manager

1901 N Dupont Highway

Biggs Data Center

New Castle, DE 19720

The results of the criminal background check will be reviewed and kept completely confidential.

NOTE: If your firm is unable to comply with the above process, please list this as an exception in Attachment 3 of the RFP. In response to this Exhibit K, please describe your firm’s process. The selected vendor will be prepared to discuss this process with the State.

Exhibit

- CMS Certification

https://www.medicaid.gov/medicaid/data-systems/certification/streamlined-modular-certification/index.html

Exhibit M

- 2015 PASRR National Report

2015 PASRR National Report Section 2, page 12

2 Level I Screens

The PASRR regulations at 42 CFR 483.100-138 give no detailed guidance about the Level I process, except that it should identify all individuals who are "suspected of having" a PASRR-relevant disability (section 483.128(a)). To develop a Level I review instrument, we followed five fundamental principles about the design of Level I tools:

1. Sensitivity: The Level I should be sensitive enough to identify all individuals who might have a PASRR disability. As such, it should generate some false positives – it should sometimes identify individuals who are later found (at Level II) not to have a PASRR disability. A Level I that generates no false positives will "miss" some individuals who do, in fact, have a PASRR disability.

2. Specificity: The Level I tool should be as specific as possible. It should screen out individuals who show no signs of having a PASRR disability. As such, it should keep the number of false positives relatively low – but not zero.

3. Usability: The tool should be easy to understand and use at the level of professional qualification the state requires. In most states, there are very few qualifications. The logic of the questions should be straightforward, not relying too much on separate instructions or training – again, commensurate with who does the screening (typically hospital staff or even NF staff) and the level of influence the state PASRR agencies have over these screeners. Each question should ask for one and only one answer. Screeners in most states must be able to complete the tool without the expert judgment that comes with years of clinical training and practice.

4. Accuracy: The tool should be accurate. For example, where the tool includes criteria for PASRR disabilities, those criteria should be correct – as with age for ID and RC.

5. Informativeness: To the extent practical, tools should capture information that would help inform the Level II evaluation (if one is necessary).

Guided by these design principles, we developed a set of 14 data elements for scoring Level I tools. These 14 elements represent “plausible triggers” – items that seem, logically, to predict the possible presence of MI, ID, or RC.

2015 PASRR National Report Section 2, page 13

Table 4 presents those data elements along with the keywords that guided our review of Level I tools. (More information about how we applied these keywords can be found in Section 2.1, Methods.)

In developing these data elements, we were informed by the Level II requirements in the CFR, but we did not replicate those requirements. Indeed, a Level I that replicates the requirements of a Level II is not a preliminary screen at all and would generate false negatives – it would fail to identify individuals who in fact have a PASRR disability.

Nonetheless, the criteria in the CFR for data required in the Level II can supply guidance about who is expected to be evaluated by Level II, and therefore the kinds of evidence Level I screeners should look for in order to identify those people. When these data elements are present, they can serve as triggers for a possible Level II evaluation, or for additional review when experienced clinicians review and approve Level I screens (before a Level II evaluation) – what is sometimes informally called a Level 1.5.

It is worth noting that data elements 4.1 and 4.2 reflect the design principle of informativeness. According to the CFR, PASRR Level II evaluations can sometimes be halted when it is determined that the individual does not have MI for PASRR purposes because dementia is also present – but this decision must be made at Level II, not Level I. The Level II can be terminated if a qualified professional determines that the individual has MI and a primary diagnosis of dementia (section 483.128(m)) that has advanced to be more prominent in the individual’s experience than the MI. States can also apply a categorical determination for individuals with MI/ID/RC who by situation obviously need NF care but would not benefit from Specialized Services (section 483.130(h)) – and categorical determinations involve abbreviated Level II evaluations. Even though categorical determinations are Level II functions, states may permit Level I screeners to apply the categories when documented evidence is available and no clinical judgment is required, or to collect this information to help inform the work of Level II evaluators or, if applicable, the “Level 1.5” approvers of the Level I.

One might imagine that a tool with all of the triggers in Table 4 would lead to a large number of false positives and, thus, an unnecessary number of Level II's – so many, in fact, that a state's Level II systems might be overwhelmed. This is a reasonable concern. However – as we will see in Section 3 – our analysis of MDS suggests that current PASRR systems generate too many false negatives, at least for MI. As recorded in MDS, PASRR identifies relatively few individuals who otherwise carry a diagnosis of at least one

2015 PASRR National Report Section 2, page 14

mental illness. We can therefore plausibly argue that Level I tools should be more "open-minded" about who should receive a Level II evaluation.

An additional element we did not examine is congruence of each state’s Level I form with any categorical determinations the state uses, and whether those categories are approved in the Medicaid state Plan. If Level I screeners are to apply categories or give the information to those who do approve categorical determinations, the Level I form must contain data elements sufficient to make and document those Level II decisions. Since an abbreviated Level II evaluation report is required for categorical determinations, (section 483.128(j)), the Level I tool, or a supplement to it, must collect all the information needed for that report.

It is important to again note that we have deliberately confined our analysis to the forms and tools states use. We have not yet assessed the policies and procedures states use to administer those tools – for example, the trainings that screeners receive or the algorithms that state use to translate responses into a probability that a Level II is warranted. The influence of these policies and procedures on the success of Level I screens remains, for now, unmeasured.

A final note about the data elements we used in our analysis. Following our 2014 analysis, some states questioned whether the data elements we had identified were strongly supported by evidence. This was especially true for two items:

1. The item about substance abuse. We included this data element because there is a high correlation between MI and substance abuse disorders.

2. Our claim that Level I's should not impose a strict "look-back period" to determine whether an episode of mental illness has previously impaired an individual's functioning. If the look-back period is too restrictive, we reasoned, PASRR may miss individuals who are at greater risk of psychiatric challenges when they enter the (sometimes stressful) environment of a nursing facility.

In further discussion with states, and in close collaboration with our partners at CMS, the PTAC team agreed with state concerns that we do not yet have Evidence-based reasons for a final conclusion that Level I should include all of the data elements in our analysis. However, it is difficult to imagine eliminating any one element without also missing some individuals, because each element identifies different populations or different needs. Whether these items really do distinguish between people with a PASRR disability and people who lack such a disability is an empirical question. For example, while we

2015 PASRR National Report Section 2, page 15

continue to find that it is too restrictive in Level I to limit the look-back period for episodes of mental illness to the same timeframe used in Level II, we do not set an alternative time frame, because we currently lack data about the most effective time frame. As states modify their Level I tools and begin using them in the field, we encourage state staff to analyze the data they get back to determine whether these items are truly discriminating. PTAC can help with designing these analyses.

In our conversations with states, we also have been made aware that they often define the age of onset for intellectual and developmental disabilities in ways that do not align with the PASRR rules. Most commonly, states set the upper age for both at 22 – usually the definition used in the states’ 1915(c) waiver programs for serving individuals with I/DD. The CFR, on the other hand, stipulates that the upper age for intellectual disabilities is 18. Our use of the CFR age boundary has created some confusion and consternation. In future analyses of Level I tools, we will accept as comprehensive any age boundary for I/DD that is equal to or greater than the age boundary set in the CFR. In other words, we will treat as comprehensive an item that stipulates that an intellectual disability must manifest by the age of 21 or 22. The only situation that would prompt us to mark that data element as partial or absent would be stipulating an age that is below the age set in the CFR (say, 12 or 15 – a situation that we believe is highly unlikely). It is the job of evaluators at Level II to determine whether an intellectual disability manifested by the age of 18, or a related condition by the age of 22. The Level I can be more open-minded about age. As we have said before, the Level I should generate some false positives, and this is a case in which false positives are acceptable.

One distinct advantage of retaining the same Level I data elements for the 2015 Report is that it allows us to compare directly between the findings of the last National Report and the findings of this one. We will therefore be able to quantify the degree to which states have incorporated these plausible data elements/triggers into their screens or are working to do so.

2015 PASRR National Report Section 2, page 16

Table 1: Data Elements for Level I Screen

| Item # | Data Element | Keywords/Phrases |
| --- | --- | --- |
| Mental Illness |  |  |
| 1.1 | Mental illness diagnosis | diagnosis; serious mental illness; mental disorder |
| 1.2 | Substance abuse disorder | substance use |
| 1.3 | Interpersonal symptoms | interpersonal; serious difficulty interacting with others; altercations, evictions, unstable employment, frequently isolated, avoids others |
| 1.4 | Completing tasks | serious difficulty completing tasks, required assistance with tasks, errors with tasks; concentration; persistence; pace |
| 1.5 | Adapting to change | self-injurious, self-mutilation, suicidal, physical violence or threats, appetite disturbance, hallucinations, delusions, serious loss of interest, tearfulness, irritability, withdrawal |
| Intellectual/Developmental Disability or Related Condition |  |  |
| 2.1 | ID/DD diagnosis | diagnosis; intellectual disability; developmental disability; mental retardation |
| 2.2 | ID/DD age of onset | age 18 (age of onset); evidence |
| 2.3 | Related condition diagnosis | evidence, history, diagnosis; affects intellectual functioning, affects adaptive functioning; autism, epilepsy, blindness, cerebral palsy, closed head injury, deaf |
| 2.4 | Related condition age of onset | age of onset; evidence; history; age 22 |
| 2.5 | Receipt of services | agency serving individuals with ID/DD; past and present; services; services received; referred/referrals |
| Key Symptoms or Behavioral Indicators |  |  |
| 3.1 | Undiagnosed condition | evidence; presenting evidence; suspected diagnosis; undiagnosed; indications |
| 3.2 | Functional limitations | mobility, self-care, self-direction, learning, understanding/use of language, capacity for living independently |
| Co-morbid Dementia |  |  |
| 4.1 | Primary dementia diagnosis | dementia; primary diagnosis |
| 4.2 | Documented evidence of primary dementia | dementia work up; comprehensive mental status exam; primary diagnosis; evidence |

2015 PASRR National Report Section 2, page 17

2.1 Methods

Notifying States of Our Analysis and Giving Them the Option to Respond: On March 18, 2015, PTAC notified states it was preparing to review state Level I tools for the 2015 National Report. PTAC sent each state the latest Level I form on file and gave states an opportunity to respond with their most recently updated Level I form. States were given until March 27 to respond with an updated Level I tool. Twenty-three (23) states responded with an updated Level I form for PTAC’s review, while the other 28 states indicated they were either in the process of updating their Level I form or were using the same form from the 2014 review. PTAC reviewed the 28 updated Level I forms sent by states, and, on August 19, sent out draft, state-specific Fact Sheets to all the PASRR leads in the three key agencies of all 50 states and the District of Columbia: the Medicaid agency, the state mental health authority, and the state intellectual disabilities authority. (With the help of CMS Regional Office staff, we maintain an updated list of these contacts. We urge states to keep this information current.) States were given the option to respond to the draft Fact Sheets with any comments or concerns by August 28. Thirteen (13) states responded with questions or a new tool. PTAC reviewed the new tools and feedback and sent newly revised Fact Sheets to 12 of the states.

The Fact Sheets are only given to each state for self-assessment purposes; they are not accessible to other states. Each Fact Sheet:

 Describes the nature of PTAC's review project.

 Lists the 14 data elements (listed below) and the state's score on each element.

 Presents a set of suggestions for revising the state’s current tool; and

 Lists the names of the tools we reviewed (to verify, one last time, that we had reviewed the state's most current tool).

It is important to note that we accepted and reviewed updated Level I screens that were still in draft form, and not yet in use in the field. In this way, we gave states as much credit as possible for the improvements they had made.

Coding the tools: Each data element in each tool was given one of three scores:

 Comprehensive: The tool captured the data element thoroughly.

 Partial: The tool captured the data element partly but incompletely, or it misstated one or more criteria (including age).

2015 PASRR National Report Section 2, page 18

Absent: The tool did not capture this data element at all.

Data elements were coded as "partial" for a variety of reasons; some of the most common reasons are listed in Table 5. (For some data elements, no single reason predominated; we have labeled these cases ʺVarious”; see Table 4 for a description of each element.) Early testing of the review instrument showed a high degree of reliability across coders.

Table 2: Common Reasons for Scores of "Partial" on Each Data Element

| Data Element | Common Reasons for "Partial" |
| --- | --- |
| 1.1 | None (no partials) |
| 1.2 | None (no partials) |
| 1.3 | Time limit placed on symptoms (e.g., last 6 months) |
| 1.4 | Time limit |
| 1.5 | Time limit |
| 2.1 | Diagnosis of ID and RC asked in the same question (should be separately) |
| 2.2 | ID age of onset stated incorrectly (should be 18) |
| 2.3 | Diagnosis of ID and RC asked in the same question |
| 2.4 | RC age of onset state incorrectly (should be 22) |
| 2.5 | Time limit placed on referrals or receipt of services |
| 3.1 | Various |
| 3.2 | Various |
| 4.1 | Tool indicates that evidence of dementia halts PASRR (i.e., no Level II) |
| 4.2 | Various |

For each state, we calculated an overall "comprehensiveness score" – the total number of data elements scored as comprehensive, divided by the total number of data elements (out of 14 altogether), taken as a percentage. Note that the distinction between "absent" and "partial" does not affect the final score – only the number of elements scored as "comprehensive" figures into this value.

Because the CFR gives little guidance about the contents of a Level I screen, comprehensiveness scores do not directly reflect compliance. Instead, they indicate the degree to which a state's Level I tool adheres to the five design principles we articulate above, and the likelihood that the Level I tool will enable the state to comply with the requirement to identify the correct individuals. Moreover, comprehensiveness scores do not capture any information about the overall operation of a state's Level I system.

2015 PASRR National Report Section 2, page 19

2.2 Findings and Discussion

The major finding of this analysis is that many states have improved the quality of their Level I tools, but that many still do not reflect the design principles we identified above. In some cases, tools were too restrictive about whether an individual might have a PASRR disability; in other cases, tools did not include some important pieces of evidence that would trigger a Level II evaluation. As Table 6 shows, the majority of states – 33, or 64.7 percent – fall in the top two quartiles. (This table is included in the Executive Summary as Table 1.) A sizable share of states – 20, or 39.2% – fall in the uppermost quartile. Table 7 lists all 51 States and the quartiles in which they scored.

These findings represent a dramatic improvement over our 2014 analysis, when the majority of states – 58.8 percent – fell within the bottom two quartiles. Clearly many states have used the feedback from the 2014 Report and modified their tools to adhere to the design principles it articulated.

Table 3: Number and Percentage of States Within Each "Comprehensiveness Quartile," with 2014 Comparison Data

| Level of Comprehensiveness | # States | % States 2015 | % States 2014 |
| --- | --- | --- | --- |
| 76%-100% | 20 | 39.2% | 11.7% |
| 51%-75% | 13 | 25.5% | 29.4% |
| 26%-50% | 16 | 31.4% | 52.9% |
| ≤ 25% | 2 | 3.9% | 5.9% |

Despite the improvements we have seen over 2014, the need for national improvement is still evident, as 18 states – more than a third – fall within the bottom two quartiles. We have been talking to lower-scoring states about why their results appear as they do, and to provide support for any changes they wish to make to their Level I screens.

The pattern of findings and state responses to the findings indicate the challenging balance required for effective Level I tools. In most states Level I screeners are not qualified to make judgments about mental illness or intellectual disability (in some states they are non-professionals); but the tool they use must have triggers to identify everyone who should be evaluated by qualified Level II evaluators. Some states with missing or overly restrictive triggers thought that only the Level II evaluation should collect information on any issues that require professional judgment – correctly preventing Level I screeners from working beyond their qualifications, but missing the point that individuals not triggered at Level I will never be presented to Level II. States with Level I tools that require too much judgment or that require the screener to make

2015 PASRR National Report Section 2, page 20

Level II decisions said they would otherwise miss individuals who need PASRR protection – correctly attempting to identify all affected individuals but introducing both false negatives and false positives by exceeding the screener’s capabilities.

The degree to which state PASRR programs might be affected by the mismatch between the design principles we have identified, and the tools states use is unknown. However, previous studies of PASRR, and impressions from most experts in the field, have long indicated that Level I is missing many individuals it should be identifying. Our analysis of MDS, presented next in Section 3, suggests that inadequacy of Level I tools is causing PASRR programs to be too conservative in identifying individuals who have serious MI.

Exhibit N

- Delaware Medicaid State Plan

1115 Demonstration Waiver; Attachment E; Medical Eligibility Determinations

Medical Eligibility Determinations

The state’s Division of Medicaid & Medical Assistance Pre-Admission Screening (PAS) team completes a level of care (LOC) screening to determine if the applicant requires the level of care LOC provided by the program. An individual must be in need of skilled or intermediate level of care as determined by PAS and as defined below in order to be medically approved for the DSHP-Plus program’s enhanced services. During the LOC determination process, the PAS Team obtains a comprehensive medical evaluation of the level of care needed in a facility or the community. Physician orders are required for skilled nursing needs. The medical evaluation must be signed and dated not more than 365 days before the date of referral for the DSHP-Plus program.

Referrals to PAS may come from the family of the applicant as well as other sources.

LOC Criteria with Implementation of DSHP-Plus – With implementation of DSHP-Plus, Delaware revised the nursing facility (NF) LOC definition for individuals entering a nursing facility to reflect that they must need assistance with at least two Activities of Daily Living (ADLs) rather than the previous minimum requirement of assistance with one ADL. There will be no impact on eligibility as a result of this change. Individuals requesting HCBS must be determined by PAS to be “at-risk” of institutionalization by requiring assistance with at least one ADL. Those Medicaid participants already residing in Nursing Facilities as of implementation of DSHP-Plus will be automatically enrolled in the DSHP-Plus program and their nursing facility services will continue to be covered by Medicaid as long as they continue to require assistance with at least one ADL.

“Activity of daily living (ADL)” means a personal or self-care skill performed, with or without the use of assistive devices, on a regular basis that enables the individual to meet basic life needs for food, hygiene, and appearance. The ADL need may look ‘independent’, but assessment will reflect, without supervision and/or assistance, clients’ ability to function and live independently, will be compromised. Assessment will reflect client’s inability to manage their own hydration, nutrition, medication management, mobility and hygiene, as applicable.

Nursing Facility Level of Care– PAS determines that an individual requires an NF LOC when the individual requires assistance with at least two ADLs. This LOC requirement only applies to individuals newly entering a NF. All individuals receiving services in a NF prior to implementation of DSHP-Plus will be grandfathered at the LOC requirement of requiring assistance with at least one ADL as long as they continue to require assistance with at least one ADL. In addition, children residing in the community are medically eligible under TEFRA if they are determined to require a NF LOC.

Exhibit O

- Review of State PASRR

National PASRR Policies and Procedures Review | June 12, 2012, | p. 11

The data elements in Table 2 assess the degree to which States fulfill each of the specific requirements of their MI and MR Level II tools. Keywords and phrases in italics were taken directly from the CFR. The remaining keywords and phrases stem from the identification of good clinical practices and are not specified in the CFR. The value for each data element was coded as comprehensive, absent, or partial (these terms are defined below).

Table 2: Data Elements for Level II

Note: All citations are to 42 CFR Part 483.

The column labeled “CFR” cites the specific section of the Code of Federal Regulations. Values in this column represent the sections of the regulation that specify the data elements, both for PASRR/MI and PASRR/MR.

Exhibit P

- State Nursing Facility Medical Necessity Criteria

Categorical Group Determinations

- Convalescent Care: Client meets the following criteria: Yes No - Admission to NF directly from hospital after receiving acute medical care. - Need for NF is required for the condition treated in hospital. Specify Conditions: _________________________________________________________________ - Lacks adequate supports to safely remain in the community for 24 hour skilled nursing observation or intervention IE: Complex wound care, IV therapy - NF stay not to exceed 120 days. Specify number of days requesting: ______________ - There is not current risk to self or others. - Does not meet all criteria for an exempted hospital discharge

- Respite: Client being admitted to provide caretakers relief and meets the following criteria: Yes No - Respite care is to provide relief to the family or caregivers - There is no current risk to self or others. - NF stay not to exceed 14 days in one year fiscal year. Specify number of days requesting: __________________________.

- Delirium : Client being provisionally admitted pending further assessment due Yes No to the presence delirium and meets the following criteria: - Accurate diagnosis cannot be made until Delirium clears. - NF stay not to exceed 7 days.

- Emergency Placement: Client is being provisionally admitted pending further Yes No assessment due to an emergency situation requiring Protective Services and meets the following criteria: - Authorization was provided by an appropriate state Protective Services Agency. Authorized by: Name:___________________________________________________ Agency:______________________________ Phone: ______________ - There is no current risk to self or others. - NF stay not to exceed 7 days.

- Terminal Illness: Does the individual meet the following criteria: Yes No - Life expectancy of less than six months (records supporting the terminal state must accompany this tool.) - There is no current risk to self or others.

- Severe Medical Dependence: Does the individual meet the following criteria: Yes No - Coma, ventilation dependence, functioning at a brain stem level, or other diagnoses which results in a level of impairment so severe that the individual would be unable to participate in a program of specialized care associated with his/her MI and/or I/DD. (Documentation of the individual’s medical status must accompany this tool.) - There is no current risk to self or others.

Exhibit Q

- Quality and Performance Reporting

EXHIBIT Q

Performance and Quality Management Program and

Service Level Agreements (SLAs)

Performance standards shall be implemented to ensure the quality of Contract Performance, provide documented performance levels in critical areas of the functionality and operations and to improve the State of DMMA (State), Department of Health and Social Services (Department or DHSS), Division of Medicaid and Medical Assistance (DMMA)’s  contract management oversight and capabilities.

Each Performance Standard - Service Level Agreement (SLA) will be measured against a set of metrics as established through negotiation between DMMA and the Vendor. The Vendor in cooperation with its Independent Contractors will provide systems, operations, and performance monitoring tools and a method for monitoring performance.  DMMA will have access to the monitoring outcomes, processes, and reporting.

Quality measures will be reported using outcomes that provide flexibility and adaptability.

DMMA may assess damages as noted below for Vendor’s failure to meet an SLA.  Vendor shall not be subject to SLAs, liquidated damages or adverse action by DMMA for SLAs that include delays, interruptions, or fault attributable to (i) events of force majeure.  Damages may be applied by DMMA in the event that the Vendor fails to meet the SLAs or the requirements of this Contract.  The Vendor agrees to pay DMMA for the specifically outlined sums as liquidated damages.

DMMA will assess damages based on its assessment of the Vendor's success in meeting required performance standards – SLAs.

DMMA will notify the Vendor in writing of the proposed damage assessment and allow the Vendor five  (5) business days to request an exception. DMMA will require the Vendor to deduct the damages by the next invoice cycle following the final notice of assessment (Performance Letter).

If the parties (DMMA or Vendor) fail to agree on a final assessment notice, disputes shall be governed by Section 11 of the Contract.

Pending final determination of any dispute, both parties shall proceed diligently with performance of the dispute Agreement.

The Vendor will be subject to meeting performance standards (SLAs) with a comparison of performance against those standards made periodically at a frequency specified by both parties.  DMMA has the right to change the frequency based on Vendor performance or DMMA policy.

The Vendor must have processes in place to monitor and self-report against all performance standards (SLAs).

The Vendor will implement a Performance Monitoring System for example, a SharePoint site to provide DMMA a method and other tools used to provide reporting of the quality and performance measurements agreed upon by DMMA and the Vendor.

Corrective Action Plans (CAPs)

Must include:

•	Issue

•	Dates and times of issue

•	Root Cause of issue

•	Proposed resolution

•	Proposed dates for completion

The first time any incident is reported or the DMMA identifies an incident, a CAP is to be created

Initial CAP to be provided in five (5) business days from knowledge of incident

DMMA and Vendor will approve CAP (CAP negotiation period allowed)

Vendor will provide status updates on periodically all open CAPs

Vendor and DMMA can make updates to the CAP while CAP is open if both parties agree (living document)

Once the CAP is closed, if the same incident and its supporting details occurs again, damages will apply immediately and there is not a second CAP for the same incident with the same details

If a CAP is closed and the same incident occurs with different supporting details, another CAP

DMMA will formally provide the Vendor a Performance Letter that addresses any performance successes, concerns, needs for CAPs and/or liquidated damages

Service Level Agreements (SLAs)

1)	Staffing – Level II Evaluators

1a.	DMMA specific annual training for vendor employees and Level II Evaluators, completed and reported timely.  The following are the trainings to be reported, Clinical Work Plan training, Complete Quality Review training, Annual HIPAA Compliance for Evaluators, Annual HIPAA compliance for Business Professionals, Ethics and Code of Conduct, and Cybersecurity

Damage: $100.00  per month per contracted Evaluators and vendor employee until completed, completion due at end of Calendar Month (CM) October

1b.	Vendor to provide the Vendor DMMA Operational Team’s organizational chart as well as key personnel directory including date of hire every month by the 15th business day of each month

Damages: $50.00 every business day that it is not submitted

1c.	Vendor to provide a listing of those newly contracted Level II Evaluators who have been directed to complete a background check within a month of a fully executed signed contract with the Level II Evaluators as defined by the DTI policies and procedures due by the 15th business day of each month

Damages: $1000.00 per instance that the newly contracted Level II Evaluators list is not provided

1d.	Vendor to provide DMMA Level II Evaluators that are at a minimum:  licensed in DMMA as an RN and have 2-years psychiatric experience or a DMMA Licensed Clinical Social Worker (LCSW) with 1- year medical experience and 2-years psychiatric experience

Damages: $1000.00 per instance of an unqualified Level II Evaluator that provided a service to a DMMA.

2)	Reporting

2a. 	In instances when required reports request combinations of data elements not represented in one of Vendor our standard on-demand reports, Vendor will create repeatable data queries as required.  Upon request from DMMA State Contract Officer or designee, Vendor will have three (3) business days from date notification sent to determine and clarify data elements, determine priority level with DMMA State Officer or designee, and agree upon delivery date for report.

Delivery timeline will be determined by priority level, as outlined below:

Priority Level	Delivery Timeline

Low	>14 business days

Medium	7 – 14 business days

Medium-High	3 - 6 business days

High	24 – 48  hours

Damages: $50.00  per calendar day the requested data query is not provided based on the predefined query delivery timeline

2b.	Vendor to provide DMMA PASRR Metrics Report to DMMA as defined at final certification, including performance self-reporting, report due end of CM February (October – December), May (January – March), August (April – June), November (July – September)

Damages: $50.00  per calendar day if report is not submitted timely

2c.	Vendor to provide DMMA Quarterly Quality Report in its entirety as spelled out in the contract due at the end of the CM February (October – December) May (January – March), August (April – June), and November (July – September)

Damages: $50.00 per calendar day the report is not submitted timely

2d.	Vendor to provide CMS Annual Report to State by March 15th of each year

Damages: $50.00 per calendar day that it is not submitted

2e.	Vendor to update and distribute any agreed upon change to the Clinical Work Plan within a month of the approval by the State Officer or designee

Damages: $50.00 per calendar day the updated Clinical Work Plan has not been distributed, beginning one month after DMMA approval

3)	System Availability

3a. 	Vendor to notify DMMA State Contract Officer or designee and DMMA end users of scheduled downtime 24 hours in advance.  Method of notification to be determined by DMMA State Officer and Vendor Program Manager.  Excluding the daily business day maintenance window scheduled.

Damages: $1000.00 per instance

3b.	Vendor to notify DMMA State Contract Officer or designee of unscheduled downtime within the first 1.5 hours that Vendor is aware of the unscheduled downtime

Damages: $1000.00 per instance

3c.	 Notification to DMMA end users will be determined by DMMA State Contract Officer or designee based on severity, Vendor to provide notification within 2 hours after State provides decision

Damages: $1000.00 per instance

4)	System Response Time

4a.	Vendor application server, will have a monthly average response time of 1 seconds or less, calculated monthly and reported to be delivered on a quarterly basis. CM February (October – December) May (January – March), August (April – June), and November (July – September)

Damages: $500.00 for each month that response time is not met

5)	System Maintenance and Operational Support

5a.	Vendor to provide the State the preplanned schedule of downtime every 6 months, February (March – August) and August (September – February) and notify DMMA within 24hours of a deployed emergency release.

Damages: $50.00 per calendar day not provided

6)	Operations Management

6a.	Vendor shall participate and provide agendas 1 business days prior to the State Call meeting and minutes within 5 business days of the meeting.

Damages: $100.00 for any instance of non-participation (Vendor does not attend scheduled meeting nor requests a cancelation), lack of agenda, and minutes

6b.	Vendor to provide DE PASRR monthly defect reporting (Bug/Product Backlog Item Tracker) and solution tracking at status meeting on the agreed upon cadence.

Damages: $100.00 per month until successfully submitted

6c.	Vendor to process Level II summary of findings in five business days from date of Level I completion with the determination of a needed Level II, 90% of the time, to be reported on a quarterly basis, CM February (October – December) May (January – March), August (April – June), and November (July – September)

Damages: $500.00 monthly for every percentage after a full percentage is not met

6d.	Level I PASRR turnaround time cannot exceed 8 business hours excluding the time a review is on hold, awaiting information, 90% of the time, to be reported on a quarterly basis, CM February (October – December) May (January – March), August (April – June), and November (July – September)

Damage: $500.00 monthly for every percentage after a full percentage is not met

6e.	Solution must be available for Level I submissions 24/7/365 except for downtime reported in advance), to be reported on a quarterly basis, CM February (October – December) May (January – March), August (April – June), and November (July – September)

Damages: $500.00 per incident excluding force majeure

6f.	Providers and Level I submitters must be able to print letters as needed 24/7/365 except for downtime reported in advance, to be reported on a quarterly basis, CM February (October – December) May (January – March), August (April – June), and November (July – September)

Damages: $500.00 per incident excluding force majeure

6g.	Vendor to schedule a meeting with DMMA and Vendor Performance/Quality Team as requested (ad hoc) within a week of request.

Damages: $200.00 for every week not scheduled, exceptions can be requested

6h.	Vendor to respond to DMMA within 30 business days with an estimate if a charge is required for any requested system change order unless an exception has been approved.

Damages: $100.00 per business days that estimate is not provided

6i.	Vendor to notify the Clinical Alignment Team of any update to the Clinical Work Plan by the last day of the month following the update for example if an update occurs in June, the notification must be provided by July 31st.

Damages: $500.00 per month that the Clinical Alignment Team members were not notified after the monthly due date

6j.	Vendor to provide CAP within 5 business days of any unscheduled down time unless there is an approved exception.

Damages: $500.00 per business day for failure to provide CAP

7)	Business Continuity and Disaster Recovery (BCDR)

7a.	Tabletop exercises are conducted annually across contracts to test and validate the effectiveness of Business Continuity and Disaster Recovery plans.  Vendor to supply results of exercise at end of Calendar Year (CY) November.

Damage: $500.00 per month until results are provided due at end of CY November

7b.	Vendor shall back up all data daily and rerun any backups that failed or partially backed up within a calendar day, to be reported on a quarterly basis, Calendar Month (CM) February (October – December) May (January – March), August (April – June), and November (July – September)

Damages: $50.00 per calendar day that data is not backed up fully

7c.	Vendor to provide updated BCDR plan annually, CY November.

Damages: $500.00 per month not provided to State

7d.	Vendor not to surpass the standard Recovery Time Objective (RTO) of 72 hours.

Damages: $1000.00 per every full hour after 72 hours

7e.	Vendor not to surpass the standard Recovery Point Objective (RPO) of 8 hours.

Damages: $1000.00 per every full hour after 8 hours

7f.	Vendor not to surpass the standard Maximum Allowable Outage (MAO) of 72 hours.

Damages: $1000.00 per every full hour after 72 hours

8)	Security

8a.	Vendor to complete a quarterly audit of active vendor system users, to be reported on a quarterly basis, CM February (October – December) May (January – March), August (April – June), and November (July – September)

Damages: $100.00 for every month after quarter end that review is not completed and reported

8b.	Vendor to monitor the applicable sections of DTI Enterprise Standards and Policies website and maintain these standards throughout the life of the Agreement. These standards are applicable to all Information Technology use throughout the State of DMMA. if the change requires a material change in operations or cost to the Vendor, DMMA and Vendor shall negotiate an equitable adjustment to the Agreement to account for such time or cost.

Damages: $1000.00 per instance, where Vendor does not have a mitigation control, Plan of Action and Milestones (POAM), or CAP in place.

8c.	Vendor to notify the State of all actual (as determined by the vendor Privacy Office) security incidents resulting in a data breach for DMMA five (5) business days and provide the State a CAP within 5 business days.

Damages: $500.00 per day for failure to provide as direct above

8d.	Vendor to complete an Independent Security Assessment annually, CM October.

Damages: $1000.00 for every month it is past due and not provided to DMMA

8e.	Vendor to provide executive summary and any POAMs created applicable to the DMMA PASRR contract and CMS within 6 weeks of receiving the final Independent Security Assessment from the independent auditor.

Damages: $500.00 per week for every week past the 6-week time period, unless there are extenuating circumstances  for a delay in the assessment process that have been communicated by vendor in writing and accepted by DMMA

8f.	Vendor to report to DMMA at the Quarterly Performance review meeting the details and status of every POAM

Damages: $500.00 for each Quarterly Performance review meeting that POAMs are not addressed with DMMA