## Workplan Form
SCP Implementation Plan
ACTION STEPS | RESPONSIBILITY | PLAN | PLAN | ACTUAL | ACTUAL | NOTES
|  | Begin by: | Complete by: | Begun by: | Completed by:
Oversee and review the procedures of the volunteers and to ensure that they comply with Federal and State of Delaware regulations for PY27 | Program Manager | 2026-07-01 | 2027-06-30
Conduct yearly Senior Companion evaluations | Program Coordinator | 2026-07-01 | 2027-09-30
Conduct National Service Criminal History Checks for applicants desiring to be Senior Companions | Program Coordinator | 2026-07-01 | 2027-05-30
Hold 20 hour pre-service orientations | SCP Team | 2026-07-01 | 2027-05-31
Hold volunteer in-services with a minimun of 24 hours total in each county | SCP Team | 2026-07-15 | 2027-06-30
Perform income eligibility annually | SCP Team | 1/15/2026 | 2027-06-30
Update Letter of Agreement/Client Care Plans annually | Program Coordinator | 2026-03-15 | 2027-06-30
Complete bi-yearly progress reports to AmeriCorps | Program Manager | 2026-07-29 | 2027-01-31
Complete monthly and quarterly reports to State of Delaware | Program Manager/Finance | 2026-07-30 | 2027-06-30
Complete monthly reports to the Executive Director | Program Manager | 2026-07-15 | 2027-06-15
Program fully staffed - hiring as needed | Program Manager | 2026-07-01 | 2027-06-30
(Please insert rows to add additional items)

## Quality Improvement Plan Form
QUALITY IMPROVEMENT PLAN | RESPONSIBILITY | PLAN | Actual | Notes
Include all steps plus preventive and contingent actions
Review bi-monthly time batches to track volunteer hours and enter data into the Volunteer Service Years (VSYs) Calculator spreadsheet | Program Manager | Increase/decrease hours to prevent under level performance of expended hours
Ensure all National Service Criminal History Checks are done on time, every time | Program Manager and Program Coordinators | Program Manager to review files prior to coordinators scheduling orientations to prevent cost disallowance
Enter volunteer hours and volunteer information to track service years | Program Manager | Data entered bi-monthly using timesheets
Review Revenue and Expenditure (R&E) reports to ensure funding is used within the 12 months of the grant | Program Manager | Obtain R&E from finance officer at least monthly and sign off requisitions | Obtain R&E from finance officer at least monthly and sign off requisitions
Review volunteer management software to track evaluations, driver license and auto insurance expiration dates | Program Manager and Program Coordinators | To maintain compliance with AmeriCorps and CIMA (volunteer insurance)
Use electronic calendar to ensure monthly/quarterly/annual reports are sent to Div. of Volunteerism | Program Manager/finance office | Maintain communication with fiscal director

## Action Steps-Prev&Cont
ACTION STEPS | RESPONSIBILITY | PLAN | PLAN | ACTUAL | ACTUAL | NOTES
Include all steps plus preventive and contingent actions |  | Begin by: | Complete by: | Begun by: | Completed by: