## Initial
DELAWARE DEPARTMENT OF NATURAL RESOURCES AND ENVIRONMENTAL CONTROL
CHANNEL MARKING INSPECTION REPORT
TO: | EXAMPLE |  |  |  | DATE: | 2025-06-15
[5 empty] | CONTRACT: | NAT 25-311 Channel Marking
FROM: | Jane Doe |  |  |  | CONTRACTOR: | Breakers LLC
| Conservation Tech V |  |  |  | PRESENT: | John Smith | Breakers LLC
| DNREC |  |  |  |  | Jane Doe | DNREC
Quarterly Inspection
PRIMARY INSPECTION: |  |  | X | Spring |  | Summer | X
|  |  |  | Fall |  | Winter
FINAL: |  |  |  | Emergency
MATERIALS PROVIDED
ITEM NO. |  | Description |  |  |  | Fixed or Floating |  | QTY.
1 |  | Baker's Channel, Buoy 13 |  |  |  | Floating |  | 1
2 |  | Baker's Channel, Buoy 14 |  |  |  | Floating |  | 1
3 |  | Baker's Channel, Buoy 15 |  |  |  | Floating |  | 1
Received by: |  |  |  |  | DNREC Staff
Date:
Markers to be replaced
|  |  |  | Lat | Long | Type |  | Work type
1 | Correct location of buoy 13 |  |  | Decimal Degrees |  | Floating |  | Correction
1.1 | Replace buoy 14 |  |  | Decimal Degrees |  | Floating |  | Replacement
1.2 | Replace light fixture on buoy 15 |  |  | Decimal Degrees |  | Floating |  | Replacement
cc: |  |  |  |  | Conservation Tech V
CONTRACTORS' REP.
Program Manager II
PAGE 1 OF 1

## Review-final
DELAWARE DEPARTMENT OF NATURAL RESOURCES AND ENVIRONMENTAL CONTROL
CHANNEL MARKING INSPECTION REPORT
TO: |  |  |  |  | DATE:
CONTRACT:
FROM: |  |  |  |  | CONTRACTOR:
| Conservation Tech V |  |  |  | PRESENT:
Quarterly Inspection
PRIMARY INSPECTION: |  |  |  | Spring |  | Summer
|  |  |  | Fall |  | Winter
FINAL: |  |  |  | Emergency
MATERIALS PROVIDED
ITEM NO. |  | Description |  |  |  | SIZE | QTY.
Received by: |  |  |  |  | DNREC Staff
Date:
Markers to be replaced
|  | LL No. | Location | Lat | Long | Type | Work type
1 | Correct location of buoy 13 |  |  | Decimal Degrees |  | Floating | Correction
1.1 | Replace buoy 14 |  |  | Decimal Degrees |  | Floating | Replacement
1.2 | Replace light fixture on buoy 15 |  |  | Decimal Degrees |  | Floating | Replacement
2 | Location corrected
2.1 | Buoy replaced on July 15, 2024
2.2 | Light replaced on July 15, 2024
3 | Please consider this a final assessment of the Summer inspection period.
3.1 | All prescribed work has been met within the standards of DNREC
cc: |  |  |  |  | Conservation Tech V
CONTRACTORS' REP.
Program Manager II
PAGE 1 OF 1